## Executive Summary
OUF Final Implementation Readiness Matrix v1.3 — Reality Baseline Warning-Closure Aligned
Dimension | Status | Interpretation
Logical/common contract freeze | READY | ouf-contracts-v1.0.0-rc3-coherence + OUF_Contract_Publication_Maturity_v1_0.yaml; contract hashes green; publication maturity uniformly INTERNAL_FREEZE_ELIGIBLE_RC
Starter-kit baseline | READY | ouf-development-starter-kit-v0.2.1; current-baseline guard and contract tests green
Canonical E2E baseline | READY | ouf-e2e-integration-spec-v0.3; 25 scenario-specific definitions, 16/16 XMA mapping, ownership complete
Development plan | READY | WBS v0.4 Semantic Aligned: 106 tasks; 0 unknown dependencies; 0 future-wave inversions; 0 cycles; 25/25 semantic E2E mapping, 0 team/module mismatches
Final strict coherence audit | PASS | Reality Baseline v1.3 delta audit: 0 blockers / 0 warnings; repository tests and semantic mapping checks green
Team mobilization | READY | Sprint 0 / Team Mobilization Pack may be issued against Reality Baseline v1.3
Contract/integration testing | READY TO START | Scenario-neutral IAM mocks and environment substitutes remain permitted
Representative acceptance / production | CONDITIONAL | Real PLAT-01..08 bindings and representative environment remain required

## Module Readiness
Stream | Current Baseline | Internal Readiness | Execution Scope | External Gates
Integration & QA | Starter v0.2.1 + E2E v0.3 + WBS v0.4 Semantic Aligned | READY | Contract harness, identity mocks, E2E drivers/evidence, normalized scenario ownership | PLAT-08 only for final representative acceptance
Authorization | PET v1.4 Development Ready + WBS v0.4 Semantic Aligned | READY | PrincipalContext, policy snapshots, fine-grained SDK, HUMAN_REQUIRED | PLAT-01/02/03/05/08
Urban API Gateway | PET v1.3 Development Ready + WBS v0.4 Semantic Aligned | READY | Boundary identity/coarse auth, route/runtime publication, egress governance | PLAT-01/02/03/04/05/08
Onboarding & THS | PET v1.5 Development Ready + WBS v0.4 Semantic Aligned | READY | Bundle compiler, WFS onboarding, Trusted Approval + Protected Operations | PLAT-01/02/03/04/05/06/08
Semantic Registry | PET v1.3 Development Ready + WBS v0.4 Semantic Aligned | READY | Exact refs, PublicationSet, historical resolution/change impact | PLAT-04/05/06/08
Ingestion Runtime | PET v1.2 Gold Standard + WBS v0.4 Semantic Aligned | READY | Run pinning, snapshot/delta, durable handoff, no-op snapshot, replay/lineage | PLAT-02/03/04/05/06/07/08
UDP / Urban Object Registry | PET v1.3 Development Ready + WBS v0.4 Semantic Aligned | READY | Durable intake, canonical identity, multi-source resolution, query governance | PLAT-04/05/06/07/08
MCP Server | v1.1 Implementation Specification + WBS v0.4 Semantic Aligned | READY | Typed capability boundary, budget/retry, THS handoff/isolation, backend clients | PLAT-01/02/03/04/05/06/08

## Platform Gates
ID | Gate | Status | Blocks Coding? | Blocks Representative Acceptance? | Rule
PLAT-01 | IAM/M2M scenario A/B/C | OPEN EXTERNAL | No | Yes | Contract/integration uses scenario-neutral identities; real scenario only for representative acceptance/production.
PLAT-02 | Issuer/JWKS/audience/claim values | OPEN EXTERNAL | No | Yes | Mocks allowed until representative environment.
PLAT-03 | Service identity lifecycle | OPEN EXTERNAL | No | Yes | Synthetic integration identities allowed; production provisioning/rotation required later.
PLAT-04 | Environment routes/endpoints | OPEN EXTERNAL | No | Yes | Logical refs/stubs permitted for integration.
PLAT-05 | Secrets/PKI | OPEN EXTERNAL | No | Yes | Secret references only until platform binding.
PLAT-06 | DB/object/log bindings | OPEN EXTERNAL | No | Yes | Testcontainers/local compatible services permitted before representative environment.
PLAT-07 | RPO/RTO/backup profile | OPEN EXTERNAL | No | Yes | Required for operational acceptance, not functional development.
PLAT-08 | Representative acceptance environment | OPEN EXTERNAL | No | Yes | Final integrated acceptance requires target-like environment.

## Acceptance Layers
Layer | Environment | Real A/B/C required? | Allowed substitutes | Exit
Contract | CI/local | NO | Frozen schemas/fixtures + alpha/beta identity mocks | Contract, projection, invariant and E2E-spec structural tests green
Integration | Shared integration cluster | NO | Mock identity provider, stub external bindings, local/Testcontainers services | Implemented canonical OUF-E2E drivers produce scenario-specific evidence
Representative acceptance | Target-like environment | YES — real binding configured | No substitute for actual IAM/routes/secrets/storage/recovery profile | 25 canonical E2E + MCP-A + THS-A + module acceptance + performance/recovery evidence

## v1.2 Changes
Prior issue | v1.2 correction | Status
RA-01 WBS cycle | MCP-008 no longer depends on THS-006; joint THS acceptance remains downstream | CLOSED
RA-02 generic E2E | E2E v0.3 defines scenario-specific preconditions/steps/assertions/evidence for all 25 | CLOSED
RA-03 003/005/006 unowned | Dedicated WBS tasks and explicit mappings added | CLOSED
RA-04 stale Starter rc2 | Starter v0.2.1 current-baseline guard is green | CLOSED
RA-05 non-atomic mapping/accountability | WBS-E2E Map + Lead Team/Evidence Owner, no ALL/range shorthand | CLOSED
RA-06 false READY status | This v1.2 replaces v1.1 only after green strict validation | CLOSED
RB12-W01 contract maturity ambiguity | Publication maturity overlay v1.0 separates publicationMaturity from legacy reconciliationState | CLOSED IN v1.3 CANDIDATE
RB12-W02 stale execution pointers | Blueprint v0.3 / Matrix v1.4 / Terminology Notice v1.1 aligned to Starter v0.2.1, E2E v0.3, WBS v0.4, Readiness v1.3 | CLOSED IN v1.3 CANDIDATE