## Executive Roadmap
OUF Development Execution Plan / Work Breakdown — v0.4 Semantic E2E Alignment
Planning basis |  |  |  | KPI | Value | Assessment
Contract baseline | ouf-contracts-v1.0.0-rc3-coherence | hygiene-only successor of rc2 |  | Total WBS tasks | 106 | Includes MCP + THS Protected Operations
Starter kit | ouf-development-starter-kit-v0.2.1 | Helm/network policy wiring corrected |  | P0 tasks | 56 | Recalibrated to milestone/release blockers only
E2E specification | ouf-e2e-integration-spec-v0.3 | canonical OUF-E2E namespace |  | Critical-path tasks | 39 | Dependency-driven cross-team integration spine
Module teams | 7 + Integration & QA | Includes MCP implementation stream |  | Future-wave inversions | 0 | Closed
Schedule model | W0–W5 relative waves | No future-wave dependency inversions |  | Canonical E2E scenarios | 25 | 25/25 scenarios; 194 semantically validated task links
Platform identity | A/B/C unresolved external gate | Mock-provider integration allowed; real binding required for representative acceptance |  | Internal blocking doc gaps | 0 | Subject to final coherence re-audit
Wave | Purpose | Tasks | Critical
W0 | Mobilization & baselines | 12 | 12
W1 | Security/config/publication foundations | 15 | 15
W2 | Core implementation | 33 | 12
W3 | Cross-module vertical slices | 18 | 7
W4 | Failure/replay/governance hardening | 16 | 8
W5 | Acceptance & release evidence | 9 | 7

## WBS
WBS ID | Team | Wave | Epic | Task | Deliverable | Contracts / Inputs | Depends On | Acceptance Criteria | E2E Coverage | CI / Release Gates | Priority | Size | Critical Path | Status | Owner | Notes
INT-001 | Integration & QA | W0 | Baseline adoption | Pin frozen shared contracts | Immutable reference to ouf-contracts-v1.0.0-rc3-coherence + freeze-manifest verification | contract-catalog; v1.0-freeze-manifest; CURRENT_STATUS.md |  | Every module build validates the same freeze manifest; no divergent shared copies. |  | contract | P0 | S | YES | Not Started
INT-002 | Integration & QA | W0 | Starter-kit rollout | Adopt common repository/CI conventions | Module adoption checklist + CI pipeline mapping | Development Starter Kit v0.2.1 | INT-001 | Each team has mapped compile/unit, contract, integration, security, E2E, performance, package and acceptance gates. |  | compile-unit; contract; integration; security; e2e; performance; package; acceptance | P0 | M | YES | Not Started
INT-003 | Integration & QA | W0 | Platform BOM | Create platform BOM binding process | Approved BOM publishing workflow with placeholders for Spring Boot/Flyway/Testcontainers exact versions | platform-version-bindings.yaml | INT-002 | No team pins a conflicting Spring Boot line; exact versions remain platform bindings. |  | compile-unit; security | P0 | M | YES | Not Started
INT-004 | Integration & QA | W0 | Environment bindings | Standardize environment-binding injection | Environment binding convention for identity, gateway, telemetry, secrets, DB and object storage refs | environment-bindings.schema.json; M2MIdentityIntegrationProfile | INT-001 | No production endpoint/secret/issuer value is hard-coded in application code. | OUF-E2E-021; OUF-E2E-023 | contract; security | P0 | M | YES | Not Started
INT-005 | Integration & QA | W0 | Observability | Roll out correlation/logging/tracing baseline | Shared logging fields + trace/correlation conventions + prohibited logging rules | CorrelationContext; ProblemDetails; starter observability baseline | INT-002 | correlationId and trace context can be followed across Gateway and module boundaries; tokens/full payloads excluded. | OUF-E2E-016; OUF-E2E-025 | integration; security | P0 | M | YES | Not Started
INT-006 | Integration & QA | W1 | Identity test harness | Operationalize two scenario-neutral IAM mocks | Reusable alpha/beta identity fixtures and normalization assertions | M2MIdentityIntegrationProfile; PrincipalContext | INT-004 | Equivalent technical identities normalize identically without A/B/C branch logic. | OUF-E2E-021 | contract; integration; security | P0 | M | YES | Not Started
INT-007 | Integration & QA | W1 | Contract test harness | Create shared producer/consumer contract test runner | Reusable test harness for JSON Schema/OpenAPI/example validation and cross-module invariants | ouf-contracts rc2; starter-kit scripts | INT-001; INT-002 | All cataloged contracts parse/validate; module examples fail CI on incompatible changes. | OUF-E2E-022 | contract | P0 | L | YES | Not Started
INT-008 | Integration & QA | W2 | Integration fixtures | Create deterministic cross-module test data factory | Versioned source/config/semantic/auth fixtures reusable by all E2E drivers | PublishedConfigurationBundle; SemanticPublicationSet; AuthorizationPolicyBundle | INT-007 | Fixtures carry exact version/hash/correlation identities and support positive + negative cases. |  | contract; integration | P1 | L | NO | Not Started
INT-009 | Integration & QA | W3 | E2E driver framework | Implement live-driver interface and evidence writer | Driver API + EvidenceRecord writer + artifact/hash capture | E2E Integration Spec v0.1; EvidenceRecord | INT-007; INT-008 | Each live scenario can produce a conformant evidence record with immutable artifact references. | OUF-E2E-017; OUF-E2E-025 | e2e; acceptance | P1 | L | NO | Not Started
INT-010 | Integration & QA | W4 | Failure injection | Standardize controlled failure/fault injection | Reusable hooks for downstream failure, control-plane degradation, policy refresh, schema drift and network denial | E2E scenarios | INT-009 | Failures are deterministic, reversible and leave audit evidence. | OUF-E2E-001; OUF-E2E-002; OUF-E2E-023; OUF-E2E-024 | integration; e2e | P1 | L | NO | Not Started
INT-011 | Integration & QA | W5 | Evidence automation | Automate release evidence package assembly | Release evidence index with CI reports, SBOM, image digest, Helm render, E2E records and unresolved issues | starter-kit evidence-package.md | INT-009 | One machine-readable evidence index per release candidate; zero BLOCKER/HIGH unresolved for acceptance. |  | package; acceptance | P0 | M | NO | Not Started
INT-012 | Integration & QA | W5 | Release governance | Run N/N+1 compatibility and freeze check | Compatibility report against rc2 or formally approved successor | compatibility policy; freeze manifest | INT-011 | No breaking shared contract change without major; historical refs remain resolvable. |  | contract; acceptance | P0 | M | NO | Not Started
AUTH-001 | Authorization | W0 | Service skeleton | Create Authorization module structure and persistence baseline | Java 21/Spring Boot modular structure + PostgreSQL/Flyway skeleton | Starter Kit; Authorization PET | INT-002; INT-003 | Build/test/health endpoints green; no IAM product-specific logic in domain layer. |  | compile-unit; db | P0 | M | YES | Not Started
AUTH-002 | Authorization | W1 | Identity normalization | Implement Identity Context Adapter to PrincipalContext | Validated token/client context -> PrincipalContext | PrincipalContext; M2MIdentityIntegrationProfile | AUTH-001; INT-006 | actorType derives from trusted identity configuration; payload cannot override; alpha/beta mocks both pass. | OUF-E2E-021 | contract; integration; security | P0 | L | YES | Not Started
AUTH-003 | Authorization | W1 | Capability catalog | Implement capability descriptor validation/catalog | Capability catalog loader and validation | CapabilityDescriptor; CapabilityManifest; MCP projection rules | AUTH-001; INT-007 | Unknown/incompatible capability fails closed; module owner remains semantic owner. | OUF-E2E-022 | contract; integration | P0 | M | YES | Not Started
AUTH-004 | Authorization | W1 | Policy lifecycle | Implement policy authoring/publication storage and immutable bundle build | AuthorizationPolicyBundle publisher + version/hash persistence | AuthorizationPolicyBundle; PolicyGrant; OrganizationScope; AssuranceRequirement | AUTH-001 | Published bundles are immutable; partial bundle never ACTIVE. |  | db; contract; integration | P0 | L | YES | Not Started
AUTH-005 | Authorization | W2 | Authorization SDK | Implement evaluate(capability, resourceContext) | Shared in-process Authorization SDK/API | PrincipalContext; ResourceContext; AuthorizationDecision | AUTH-002; AUTH-003; AUTH-004 | Default deny; explicit deny overrides; decision returns reasonCode/policyVersion/hash. | OUF-E2E-007; OUF-E2E-015; OUF-E2E-016; OUF-E2E-018; OUF-E2E-022 | unit; contract; integration | P1 | XL | NO | Not Started
AUTH-006 | Authorization | W2 | ABAC controls | Implement org/assurance/resource-condition evaluation | RBAC + minimal ABAC evaluator | OrganizationScope; AssuranceRequirement; ResourceContext | AUTH-005 | Supported scope/assurance conditions evaluate deterministically and fail closed on missing required context. | OUF-E2E-007; OUF-E2E-016 | unit; integration | P1 | L | NO | Not Started
AUTH-007 | Authorization | W2 | Policy snapshot/cache | Implement immutable local snapshot refresh with atomic swap | Initial pull + pointer polling + build/validate/atomic swap | AuthorizationPolicyBundle | AUTH-004; AUTH-005 | Ordinary request path has no synchronous registry dependency; one request uses one snapshot. | OUF-E2E-018 | integration; performance | P1 | L | NO | Not Started
AUTH-008 | Authorization | W2 | Audit evidence | Implement PolicyEvaluationEvidence | Security/audit evidence adapter | AuthorizationDecision; PolicyEvaluationEvidence | AUTH-005 | Evidence records subject/actor/capability/decision/policyVersion/hash without token/full payload. | OUF-E2E-007; OUF-E2E-016; OUF-E2E-018; OUF-E2E-025 | integration; security | P1 | M | NO | Not Started
AUTH-009 | Authorization | W3 | Human-required guard | Implement HUMAN_REQUIRED eligibility rules | Actor eligibility guard | CapabilityDescriptor; PrincipalContext | AUTH-005 | AI_AGENT/MCP_SERVER/SERVICE_IDENTITY cannot satisfy HUMAN_USER confirmation. | OUF-E2E-014; OUF-E2E-016; OUF-E2E-021 | integration; security; e2e | P1 | M | NO | Not Started
AUTH-010 | Authorization | W3 | Directory failure semantics | Implement fail-closed directory/lookup timeouts | Bounded directory adapter + failure policy | Authorization PET external directory behavior | AUTH-006 | Required lookup timeout/unavailability produces DENY, not degraded ALLOW. |  | integration; resilience | P1 | M | NO | Not Started
AUTH-011 | Authorization | W4 | Backend integration kit | Integrate SDK into UDP/Onboarding/Ingestion/Semantic backend filters | Shared security filter integration examples/tests | PrincipalContext; ResourceContext; AuthorizationDecision | AUTH-005; AUTH-007 | Gateway allow cannot bypass backend deny; domain guard remains after authorization. | OUF-E2E-007; OUF-E2E-014; OUF-E2E-018 | integration; e2e | P0 | L | NO | Not Started
AUTH-012 | Authorization | W5 | Hardening & acceptance | Security/performance/compatibility hardening | Load tests, denial-path suite, policy refresh concurrency evidence | E2E v0.3; starter kit | AUTH-011; INT-010 | All Authorization-owned E2E assertions green; no HIGH/BLOCKER security issue. |  | security; performance; acceptance | P0 | L | YES | Not Started
GW-001 | Urban API Gateway | W0 | Gateway baseline | Create governed Gateway configuration repository and deployment skeleton | APISIX/Gateway config repo + CI validation skeleton | CapabilityManifest; RouteBinding; Starter Kit | INT-002; INT-003 | No consumer-facing route can merge without capabilityId, auth binding and backend binding. |  | compile-unit; contract | P0 | M | YES | Not Started
GW-002 | Urban API Gateway | W1 | Identity boundary | Implement scenario-neutral OIDC/OAuth2 validation binding | Issuer/JWKS/audience mapping -> normalized Gateway authorization context | M2MIdentityIntegrationProfile; GatewayAuthorizationContext | GW-001; INT-006; AUTH-002 | Alpha/beta mock identity profiles accepted per binding; no A/B/C branch in route logic. | OUF-E2E-016; OUF-E2E-021 | contract; integration; security | P0 | L | YES | Not Started
GW-003 | Urban API Gateway | W1 | Capability publication | Implement CapabilityManifest validation and route linkage | Capability manifest compiler/validator | CapabilityManifest; CapabilityDescriptor | GW-001; AUTH-003 | Every consumer-facing endpoint resolves to exactly one registered capability. | OUF-E2E-008; OUF-E2E-013; OUF-E2E-022 | contract; integration | P0 | L | YES | Not Started
GW-004 | Urban API Gateway | W2 | Runtime publication | Implement RouteBinding/SourceRuntimeProfile/ExtractionRuntimeProfile materialization | Versioned runtime projection ingestion and referential integrity checks | SourceRuntimeProfile; ExtractionRuntimeProfile; RouteBinding | GW-001; ONB-008 | Only approved runtime artifacts activate; unresolved refs fail closed. | OUF-E2E-005; OUF-E2E-017; OUF-E2E-024 | contract; integration | P0 | XL | YES | Not Started
GW-005 | Urban API Gateway | W2 | Northbound enforcement | Implement token/audience/scope/capability coarse enforcement | Northbound security policy | CapabilityManifest; GatewayAuthorizationContext | GW-002; GW-003 | Default deny for unpublished route/capability; no wildcard grant across raw/history/export. | OUF-E2E-013; OUF-E2E-016; OUF-E2E-018; OUF-E2E-022 | integration; security | P1 | L | NO | Not Started
GW-006 | Urban API Gateway | W2 | Southbound egress | Implement registry-bound egress and SSRF/DNS/redirect protection | Default-deny egress policy + endpointRef resolver | SourceRuntimeProfile; RouteBinding | GW-004 | Client cannot supply arbitrary host/port; direct source bypass is blocked. | OUF-E2E-005; OUF-E2E-023 | security; integration; e2e | P1 | XL | NO | Not Started
GW-007 | Urban API Gateway | W2 | Connector handoff | Implement GatewayConnectorHandoff | Validated native payload/reference handoff to Connector/Adapter | GatewayConnectorHandoff; SourceSchemaBinding | GW-004; GW-005 | Handoff carries exact source/schema/extraction/correlation/principal context; Gateway does not build CDE. | OUF-E2E-002; OUF-E2E-017 | contract; integration | P1 | L | NO | Not Started
GW-008 | Urban API Gateway | W2 | Error/correlation | Implement canonical ProblemDetails and correlation propagation | Error mapper + correlation/request ID policy | ProblemDetails; CorrelationContext | INT-005; GW-005 | Backend code/Retry-After/correlation preserved without semantic redirect. | OUF-E2E-016; OUF-E2E-018; OUF-E2E-025 | contract; integration | P0 | M | YES | Not Started
GW-009 | Urban API Gateway | W3 | Streaming/payload controls | Implement bounded streaming, size/content-type/timeouts/rate limits | Per-capability transport controls | Gateway PET runtime controls | GW-005 | 413/415/429/503 behavior bounded; full payload not logged. |  | integration; security; performance | P1 | L | NO | Not Started
GW-010 | Urban API Gateway | W3 | Schema preflight passthrough | Implement technical schema indicator preservation | Preflight/discovery passthrough | SourceSchemaBinding | GW-004; GW-008 | schemaVersion/fingerprint/ETag preserved; no drift classification or bundle mutation. | OUF-E2E-001 | integration; e2e | P0 | M | NO | Not Started
GW-011 | Urban API Gateway | W3 | Controlled publication | Implement validate/compile/diff/apply/verify ACTIVE lifecycle | GatewayPublicationManifest + last-known-good management | GatewayPublicationManifest | GW-003; GW-004 | Unverified config never ACTIVE; degraded control plane blocks new activation. | OUF-E2E-024 | integration; resilience; e2e | P0 | XL | NO | Not Started
GW-012 | Urban API Gateway | W4 | Backend context propagation | Propagate normalized principal/actor/capability/policy metadata | Internal security context propagation | GatewayAuthorizationContext; PrincipalContext | GW-002; AUTH-007 | Backend receives auditable context; tokens are not application payload; backend re-evaluates fine-grained auth. | OUF-E2E-014; OUF-E2E-016; OUF-E2E-018; OUF-E2E-021; OUF-E2E-025 | integration; security | P0 | L | YES | Not Started
GW-013 | Urban API Gateway | W5 | Gateway acceptance | Run E2E, fault and performance suite | Gateway acceptance evidence | E2E v0.3; starter kit | GW-006; GW-007; GW-008; GW-010; GW-011; GW-012; INT-010 | Gateway-owned E2E scenarios green; last-known-good and bypass-prevention evidence captured. | OUF-E2E-023; OUF-E2E-024 | e2e; performance; acceptance | P0 | L | YES | Not Started
ONB-001 | Onboarding & THS | W0 | Service skeleton | Create Onboarding modular service + persistence/migrations | Java 21/Spring Boot/PostgreSQL/Flyway baseline | Starter Kit; Onboarding PET | INT-002; INT-003 | State model/migrations build from zero; no duplicate IAM/secret/gateway infrastructure. |  | compile-unit; db | P0 | M | YES | Not Started
ONB-002 | Onboarding & THS | W1 | Source configuration core | Implement source definitions/bindings and version lifecycle | Source configuration aggregate + optimistic locking | SourceRuntimeProfile; SourceSchemaBinding | ONB-001 | Source config versions are immutable once published; environment promotion is explicit. |  | unit; db; contract | P0 | L | YES | Not Started
ONB-003 | Onboarding & THS | W1 | Extraction & sync | Implement ExtractionProfile and SyncProfile authoring/validation | Technical extraction/sync configuration | ExtractionProfile; SyncProfile | ONB-002 | PULL technical projection compiles filters/projection/paging/incremental settings; semantic rationale excluded. | OUF-E2E-005 | contract; integration | P0 | L | YES | Not Started
ONB-004 | Onboarding & THS | W1 | Identity & temporal mapping | Implement source-object identity and temporal/change profiles | SourceObjectIdentityPolicy + TemporalMapping + ChangeRepresentationProfile | SourceObjectIdentityPolicy; TemporalMapping; ChangeRepresentationProfile | ONB-002 | sourceObjectId remains source identity; no UrbanObjectId creation; open-ended/derived temporal rules explicit. | OUF-E2E-006; OUF-E2E-020 | contract; unit | P0 | L | YES | Not Started
ONB-005 | Onboarding & THS | W2 | Semantic/relationship mapping | Implement governed SemanticMapping/RelationshipMapping authoring | Source-specific semantic and relation mappings referencing exact Registry refs | SemanticMapping; RelationshipMapping; SemanticReference | ONB-002; SEM-004 | Mappings pin exact semantic refs; Registry TBox not copied into Onboarding. | OUF-E2E-005; OUF-E2E-019 | contract; integration | P0 | XL | YES | Not Started
ONB-006 | Onboarding & THS | W2 | Authority/access metadata | Implement authority and data-access policy publication | AuthorityPolicyDescriptor + DataAccessPolicy configuration | AuthorityPolicyDescriptor; DataAccessPolicy | ONB-002; AUTH-003 | Classification/authority metadata published; final enforcement/conflict resolution remains Authorization/UDP. | OUF-E2E-006; OUF-E2E-007 | contract; integration | P1 | M | NO | Not Started
ONB-007 | Onboarding & THS | W2 | Bundle compiler | Implement immutable PublishedConfigurationBundle compiler/checksum | PublishedConfigurationBundle build/validate/version/hash | PublishedConfigurationBundle | ONB-003; ONB-004; ONB-005; ONB-006 | Bundle is single immutable runtime execution contract; consumers need no internal table reconstruction. | OUF-E2E-005; OUF-E2E-007; OUF-E2E-017; OUF-E2E-019 | contract; integration | P1 | XL | NO | Not Started
ONB-008 | Onboarding & THS | W2 | Runtime projections | Publish Gateway SourceRuntime/ExtractionRuntime/RouteBinding projections | Approved runtime projection publication | SourceRuntimeProfile; ExtractionRuntimeProfile; RouteBinding | ONB-007 | Gateway receives technical runtime view only; semantic mapping/classification does not enter route logic. | OUF-E2E-005; OUF-E2E-017; OUF-E2E-024 | contract; integration | P1 | L | NO | Not Started
ONB-009 | Onboarding & THS | W3 | THS workspace | Implement Trusted Approval Workspace | OUF-controlled HUMAN_USER approval UI/backend boundary | TrustedHumanCardModel; Authorization contracts | ONB-001; AUTH-009 | Exact diff/hash/version shown; confirm/approve/activate uses direct user-bound Gateway/backend path. | OUF-E2E-005; OUF-E2E-014 | integration; security | P0 | XL | YES | Not Started
ONB-010 | Onboarding & THS | W3 | Approval challenge integrity | Implement ApprovalChallenge hash/ETag/state TOCTOU controls | Challenge create/link/consume lifecycle | THS boundary; module approval state | ONB-009 | Stale or changed context invalidates approval; one-time server-side consumption. | OUF-E2E-005; OUF-E2E-014 | integration; security; e2e | P0 | L | NO | Not Started
ONB-011 | Onboarding & THS | W3 | Schema surveillance | Implement technical preflight analysis and drift classification | Schema surveillance issue/classification workflow | SourceSchemaBinding; PublishedConfigurationBundle | ONB-003; GW-010 | Classification is Runtime/Onboarding-owned; breaking drift cannot silently mutate ACTIVE bundle. | OUF-E2E-001 | integration; e2e | P0 | L | YES | Not Started
ONB-012 | Onboarding & THS | W3 | Delta contract validation | Enforce DELTA_PATCH prerequisites | DeltaPatchContract compiler/validation gate | DeltaPatchContract; ChangeRepresentationProfile | ONB-004; ONB-007 | DELTA_PATCH activation fails closed without valid precompiled contract. | OUF-E2E-004 | contract; integration; e2e | P0 | M | NO | Not Started
ONB-013 | Onboarding & THS | W4 | Historical resolution | Implement immutable historical bundle/config resolution | Historical lookup API/storage behavior | PublishedConfigurationBundle; semantic refs | ONB-007 | Old bundle/config versions remain resolvable for replay; no silent current substitution. | OUF-E2E-001; OUF-E2E-015 | integration; e2e | P0 | L | NO | Not Started
ONB-014 | Onboarding & THS | W5 | Onboarding/THS acceptance | Run governance, runtime-publication and drift/replay suite | Acceptance evidence | E2E v0.3 | ONB-010; ONB-011; ONB-012; ONB-013; INT-010 | All Onboarding/THS-owned E2E assertions green; no protected operations exposed through MCP. | OUF-E2E-001 | e2e; security; acceptance | P0 | L | YES | Not Started
SEM-001 | Semantic Registry | W0 | Service skeleton | Create semantic registry modular service + persistence | Java 21/Spring Boot/PostgreSQL/Jena-compatible domain skeleton | Starter Kit; Semantic PET | INT-002; INT-003 | Artifact/revision persistence builds from zero; no graph DB/triple-store requirement introduced. |  | compile-unit; db | P0 | M | YES | Not Started
SEM-002 | Semantic Registry | W1 | Artifact/revision model | Implement semantic artifact identity, revisions and immutable published content | ArtifactDetail + ArtifactRevision APIs/store | ArtifactDetail; ArtifactRevision; SemanticReference | SEM-001 | semanticId separate from technical artifact/revision IDs; published revision immutable. |  | contract; db | P0 | L | YES | Not Started
SEM-003 | Semantic Registry | W1 | Search/get | Implement ACTIVE search and exact get/resolve | SearchResult + exact reference resolution | SearchResult; SemanticReference | SEM-002 | Search ranking is advisory; exact get never substitutes latest/current silently. | OUF-E2E-005; OUF-E2E-015 | contract; integration | P0 | L | YES | Not Started
SEM-004 | Semantic Registry | W1 | Publication sets | Implement SemanticPublicationSet compiler/hash/atomic ACTIVE pointer | Immutable publication set + deterministic manifest hash | SemanticPublicationSet; SemanticPublicationMember | SEM-002 | Membership immutable after publish; ACTIVE switch atomic; historical set remains resolvable. | OUF-E2E-005; OUF-E2E-015; OUF-E2E-019 | contract; db; integration | P0 | XL | YES | Not Started
SEM-005 | Semantic Registry | W2 | Discovery abstraction | Implement governed discovery request/provider adapter | DiscoveryRequest + provider port | DiscoveryRequest | SEM-003 | Discovery does not create official semantic artifacts automatically. |  | integration | P1 | L | NO | Not Started
SEM-006 | Semantic Registry | W2 | Candidate adoption | Implement candidate snapshot/origin/adoption workflow | DiscoveryCandidate + ExternalOrigin persistence | DiscoveryCandidate; ExternalOrigin | SEM-005 | candidateId never becomes semanticId merely by discovery; adopted snapshot remains locally resolvable. |  | contract; integration | P1 | L | NO | Not Started
SEM-007 | Semantic Registry | W2 | Change impact | Implement SemanticChangeNotice + ImpactReport | Breaking-change detection record and consumer impact report | SemanticChangeNotice; ImpactReport | SEM-002; SEM-004 | Breaking change does not auto-remap Onboarding or rewrite historical data. |  | contract; integration | P1 | L | NO | Not Started
SEM-008 | Semantic Registry | W3 | Migration proposals | Implement governed SemanticMigrationProposal | Migration proposal workflow | SemanticMigrationProposal | SEM-007 | Proposal is advisory/governable; no automatic consumer/data migration. |  | integration | P1 | M | NO | Not Started
SEM-009 | Semantic Registry | W4 | Authorization integration | Apply backend fine-grained authorization and audit | Security filter + Authorization SDK integration | PrincipalContext; AuthorizationDecision | AUTH-011; SEM-003 | Gateway coarse allow does not expose restricted semantic operations; publication/human actions remain human-bound. |  | integration; security | P0 | M | YES | Not Started
SEM-010 | Semantic Registry | W5 | Semantic acceptance | Run publication pin/historical/change suite | Acceptance evidence | E2E v0.3 | SEM-004; SEM-007; SEM-008; SEM-009; INT-010 | E2E-05/06 pass with exact refs; no invented fallback semantics. | OUF-E2E-015; OUF-E2E-019 | e2e; acceptance | P0 | L | YES | Not Started
ING-001 | Ingestion Runtime | W0 | Runtime skeleton | Create ingestion service, job state and migrations | Java 21/Spring Boot/PostgreSQL/Flyway runtime skeleton | Starter Kit; Ingestion PET | INT-002; INT-003 | runtime_job/checkpoint/outbox baseline migrates from zero; service has no public direct source egress. |  | compile-unit; db | P0 | L | YES | Not Started
ING-002 | Ingestion Runtime | W2 | Run context | Implement run creation with pinned bundle/schema/semantic refs | Immutable run execution context | PublishedConfigurationBundle; SemanticPublicationSet | ING-001; ONB-007; SEM-004 | One run pins exact config/semantic refs through pause/resume/retry. | OUF-E2E-005; OUF-E2E-017; OUF-E2E-019 | contract; integration | P0 | XL | YES | Not Started
ING-003 | Ingestion Runtime | W2 | Connector/Adapter | Implement native payload parsing/adaptation into CanonicalDataEnvelope | Connector/Adapter ports + CDE builder | CanonicalDataEnvelope; SourceSchemaBinding | ING-001; GW-007 | CDE required fields/correlation/provenance populated; Gateway does not perform this transformation. | OUF-E2E-005; OUF-E2E-017; OUF-E2E-020 | contract; integration | P0 | XL | YES | Not Started
ING-004 | Ingestion Runtime | W2 | Sync strategies | Implement snapshot/incremental paging/checkpoint semantics | PULL sync execution engine | ExtractionProfile; SyncProfile | ING-002; ONB-003 | Concurrency/checkpoint behavior preserves ordering/coherence; rate-limits respected. | OUF-E2E-003 | integration; performance | P0 | XL | YES | Not Started
ING-005 | Ingestion Runtime | W3 | Change handlers | Implement FULL_SNAPSHOT / DELTA_PATCH / PROPERTY_EVENTS handlers | ChangeRepresentationHandler implementations | ChangeRepresentationProfile; DeltaPatchContract | ING-003; ONB-012 | DELTA_PATCH uses approved mapping only; absent legacy profile defaults only as frozen contract allows. | OUF-E2E-003; OUF-E2E-004 | contract; integration | P0 | XL | YES | Not Started
ING-006 | Ingestion Runtime | W2 | Durable handoff | Implement durable handoff/outbox/checkpoint/watermark | Handoff persistence + downstream delivery semantics | HandoffPayload; LineageRecord | ING-004; ING-003 | Committed watermark advances only after downstream durable criteria; replay/idempotency preserved. | OUF-E2E-002; OUF-E2E-004; OUF-E2E-017 | db; integration; e2e | P1 | XL | NO | Not Started
ING-007 | Ingestion Runtime | W2 | Lineage | Implement LineageRecord generation and propagation | Lineage persistence/emit path | LineageRecord; CorrelationContext | ING-002; ING-003 | run/ingestion/handoff/source/contracts/times/outcome consistent and historically resolvable. | OUF-E2E-006; OUF-E2E-015; OUF-E2E-017; OUF-E2E-019; OUF-E2E-020; OUF-E2E-025 | contract; integration | P1 | L | NO | Not Started
ING-008 | Ingestion Runtime | W3 | Retry/backpressure | Implement bounded retry, idempotency, circuit/backpressure semantics | Retry/lease/backpressure policies | Ingestion PET | ING-004; ING-006 | No retry on authorization/capability mismatch/human-required; downstream saturation bounded. | OUF-E2E-002; OUF-E2E-004 | integration; resilience; performance | P1 | L | NO | Not Started
ING-009 | Ingestion Runtime | W3 | Schema surveillance runtime | Implement preflight token observation + remediation handoff | Runtime schema-surveillance adapter | SourceSchemaBinding; ProblemDetails | GW-010; ONB-011 | Technical indicators preserved; classification delegated to Runtime/Onboarding rules; active bundle not mutated silently. | OUF-E2E-001 | integration; e2e | P0 | M | YES | Not Started
ING-010 | Ingestion Runtime | W4 | Historical replay | Implement replay against original contract chain | Replay service | LineageRecord; PublishedConfigurationBundle; SemanticReference | ING-007; ONB-013; SEM-004 | Original refs resolved; unavailable historical ref fails explicitly; replay remains auditable. | OUF-E2E-015 | integration; e2e | P0 | XL | YES | Not Started
ING-011 | Ingestion Runtime | W4 | Security/observability | Finalize M2M, correlation and protected logging | Service identity integration + structured logs/traces | M2MIdentityIntegrationProfile; PrincipalContext; CorrelationContext | AUTH-002; INT-005 | No trusted-zone bypass; no secret material in DB/logs; correlation reaches lineage. | OUF-E2E-023; OUF-E2E-025 | security; integration | P0 | M | YES | Not Started
ING-012 | Ingestion Runtime | W5 | Ingestion acceptance | Run bootstrap/delta/retry/drift/replay/downstream failure suite | Acceptance evidence | E2E v0.3 | ING-005; ING-006; ING-009; ING-010; ING-011; INT-010 | All Ingestion-owned E2E assertions green and performance/backpressure evidence complete. | OUF-E2E-001; OUF-E2E-002; OUF-E2E-004; OUF-E2E-015 | e2e; performance; acceptance | P0 | L | YES | Not Started
UDP-001 | UDP / Urban Object Registry | W0 | UDP skeleton | Create UDP modular codebase, PostgreSQL/PostGIS and worker profiles | udp-api/materializer/resolution/maintenance profiles in one modular codebase | Starter Kit; UDP PET | INT-002; INT-003 | DB migrations and workload profiles green; no premature microservice split. |  | compile-unit; db | P0 | XL | YES | Not Started
UDP-002 | UDP / Urban Object Registry | W1 | Urban Object Registry | Implement canonical UrbanObject persistence and identity model | Canonical object repository/domain model | UDP PET; SourceObjectIdentityPolicy downstream evidence | UDP-001 | UrbanObjectId is UDP-owned and distinct from sourceObjectId. | OUF-E2E-006; OUF-E2E-020 | unit; db | P0 | XL | YES | Not Started
UDP-003 | UDP / Urban Object Registry | W2 | Durable intake | Implement HandoffPayload intake and Durable ACK authority | Durable handoff receiver + receipt/recovery semantics | HandoffPayload; LineageRecord | UDP-001; ING-006 | ACK only after durable payload/reference + recovery metadata persistence; Gateway 202 irrelevant to watermark. | OUF-E2E-002; OUF-E2E-017 | contract; db; integration | P0 | XL | YES | Not Started
UDP-004 | UDP / Urban Object Registry | W3 | Materialization | Implement full/delta/property-event canonical materialization | Canonical write pipeline | CanonicalDataEnvelope; ChangeRepresentationProfile; DeltaPatchContract | UDP-002; UDP-003; ING-005 | Physical indexes/materialization remain UDP-owned; change semantics consistent with approved logical contract. | OUF-E2E-003; OUF-E2E-004; OUF-E2E-005; OUF-E2E-017 | integration; db | P0 | XL | YES | Not Started
UDP-005 | UDP / Urban Object Registry | W2 | Provenance/lineage | Persist source identity, authority and semantic provenance | Provenance/lineage model | LineageRecord; SemanticReference; AuthorityPolicyDescriptor | UDP-002; ING-007 | Exact source/semantic/authority refs retained; historical explanation possible. | OUF-E2E-006; OUF-E2E-019; OUF-E2E-020; OUF-E2E-025 | contract; integration | P0 | L | YES | Not Started
UDP-006 | UDP / Urban Object Registry | W2 | Object resolution | Implement canonical object resolution and candidate handling | Object resolver worker/ports | UDP PET; RelationshipMapping | UDP-002; UDP-005 | Only UDP assigns/merges canonical identity; source IDs remain provenance. | OUF-E2E-006; OUF-E2E-014; OUF-E2E-020 | integration | P1 | XL | NO | Not Started
UDP-007 | UDP / Urban Object Registry | W3 | Relationship materialization | Implement relationship edge materialization/resolution | ABox relationship pipeline | RelationshipMapping; SemanticReference | UDP-004; UDP-006; SEM-004 | Registry relation semantics referenced exactly; Onboarding resolution strategy respected; UDP owns instantiated edge. |  | integration | P1 | L | NO | Not Started
UDP-008 | UDP / Urban Object Registry | W4 | Fine-grained access | Integrate Authorization SDK before serialization | ResourceContext builders + access enforcement | ResourceContext; DataAccessLabel; AuthorizationDecision | AUTH-011; UDP-002 | Object/property/geometry/relation/raw/history/lineage/export controls enforced before serialization. | OUF-E2E-007; OUF-E2E-014; OUF-E2E-018 | integration; security | P0 | XL | YES | Not Started
UDP-009 | UDP / Urban Object Registry | W4 | Serving capabilities | Implement typed object/search/graph/spatial/history/lineage capability handlers | Backend capability endpoints/handlers | CapabilityDescriptor; ProblemDetails | UDP-002; UDP-007; UDP-008 | Capabilities remain typed/bounded; no Gateway/MCP SQL generation dependency. | OUF-E2E-008; OUF-E2E-012; OUF-E2E-013 | contract; integration | P1 | XL | NO | Not Started
UDP-010 | UDP / Urban Object Registry | W4 | Query Complexity Governor | Implement budget/cost admission and bounded workload enforcement | UDP Query Governor | UDP PET | UDP-009 | Governor independent from Gateway rate limits and MCP orchestration budget; structured rejection. | OUF-E2E-008; OUF-E2E-012; OUF-E2E-013 | integration; performance; e2e | P0 | XL | NO | Not Started
UDP-011 | UDP / Urban Object Registry | W4 | Raw/history/export separation | Implement separate capabilities/result scopes | Separate handlers/policies for raw/history/lineage/export | CapabilityDescriptor; AuthorizationDecision | UDP-008; UDP-009 | No wildcard/fallback from object.read to raw/history/export. | OUF-E2E-007 | integration; security | P0 | L | NO | Not Started
UDP-012 | UDP / Urban Object Registry | W4 | Historical/replay support | Support historical refs and replay-safe materialization | Historical lookup + deterministic replay support | LineageRecord; SemanticPublicationSet | UDP-005; ING-010 | Historical contract chain remains explainable; replay does not silently use current ACTIVE. | OUF-E2E-015; OUF-E2E-019 | integration; e2e | P0 | L | YES | Not Started
UDP-013 | UDP / Urban Object Registry | W4 | Storage/lake integration | Implement object-storage adapter and integrity/checksum rules | RAW/NORMALIZED/CURATED/export adapter via port | UDP PET storage contract | UDP-003; INT-004 | No silent overwrite; checksum/content-length verified; storage endpoint remains environment binding. |  | integration; resilience | P1 | L | NO | Not Started
UDP-014 | UDP / Urban Object Registry | W5 | UDP acceptance | Run materialization/auth/query/replay/failure suite | Acceptance evidence | E2E v0.3 | UDP-010; UDP-011; UDP-012; UDP-013; INT-010 | UDP-owned E2E scenarios green; governor, authorization and historical evidence complete. | OUF-E2E-002; OUF-E2E-003; OUF-E2E-004; OUF-E2E-014; OUF-E2E-015 | e2e; performance; acceptance | P0 | XL | YES | Not Started
MCP-001 | MCP Server | W0 | Service baseline | Initialize MCP Server v1.1 implementation repository | Java 21/Spring Boot modular monolith skeleton + PostgreSQL/Flyway | MCP Server v1.1; Starter Kit v0.2.1 | INT-002; INT-003 | Repository builds with mcp-server and maintenance-worker profiles; no agent/LLM runtime introduced. |  | compile-unit; db | P0 | L | YES | Not Started
MCP-002 | MCP Server | W1 | Capability manifest | Implement canonical capability registry and typed validation | Manifest loader/validator + typed DTO registry | McpCanonicalCapabilityManifest; MCP projection rules | MCP-001; AUTH-003; GW-003 | Only ACTIVE/toolEligible capabilities register; mismatch/unknown input fails before backend query. | OUF-E2E-008; OUF-E2E-013; OUF-E2E-022 | contract; integration | P0 | XL | YES | Not Started
MCP-003 | MCP Server | W2 | Authorization context | Implement server-side auth context and backend invocation boundary | Caller/session validation + governed backend client abstraction | PrincipalContext; GatewayAuthorizationContext; AuthorizationDecision | MCP-001; AUTH-005; GW-005 | tools/list is not authorization; each tools/call is re-authorized; no backend URL from client. | OUF-E2E-007; OUF-E2E-014; OUF-E2E-021; OUF-E2E-022; OUF-E2E-023 | integration; security | P0 | L | YES | Not Started
MCP-004 | MCP Server | W2 | Budget store | Implement shared cumulative Agent Budget Store | PostgreSQL/Flyway budget/session/attempt state | MCP Server v1.1 budget semantics | MCP-001 | Budget state consistent across pods and concurrent requests; bounded DB use. | OUF-E2E-009; OUF-E2E-010; OUF-E2E-011; OUF-E2E-012 | db; integration; performance | P1 | XL | NO | Not Started
MCP-005 | MCP Server | W2 | Retry/remediation | Implement RetryLoopGuard and remediation | Equivalent retry detection + explicit preferred-alternative metadata | ProblemDetails; MCP Server v1.1 | MCP-002; MCP-004 | No auto-redirect; equivalent retries stop with TOOL_SELECTION_STALLED. | OUF-E2E-008; OUF-E2E-009; OUF-E2E-013 | integration; e2e | P1 | L | NO | Not Started
MCP-006 | MCP Server | W2 | Backend clients | Implement typed clients for UDP/Onboarding/Ingestion/Semantic | Gateway-mediated capability clients | CapabilityManifest; ProblemDetails | MCP-002; MCP-003; GW-008 | No direct DB/provider access; errors and Retry-After preserved. | OUF-E2E-005; OUF-E2E-007; OUF-E2E-008; OUF-E2E-012; OUF-E2E-013; OUF-E2E-023; OUF-E2E-025 | integration | P0 | XL | YES | Not Started
MCP-007 | MCP Server | W3 | Trusted human handoff | Implement ApprovalChallenge create/link handoff | Opaque trustedApprovalRef flow | THS boundary; McpCanonicalCapabilityManifest | MCP-003; ONB-010 | MCP can prepare/link challenge only; no confirm/approve/activate/publish via tools/call. | OUF-E2E-005; OUF-E2E-014 | security; e2e | P0 | L | YES | Not Started
MCP-008 | MCP Server | W4 | Protected-operation isolation | Enforce no protected-log tools/resources/prompts/results | Registry/startup guards + result minimization | MCP Server v1.1 MCP-A53..55 | MCP-002; THS-001; THS-002; THS-005 | Protected operations absent from MCP surface and no PII log payload/resultRef reaches client. | OUF-E2E-016 | security; e2e | P0 | M | YES | Not Started |  | No dependency on THS-006 acceptance; MCP isolation is implemented before joint THS acceptance to avoid circular gating.
MCP-009 | MCP Server | W4 | Observability & maintenance | Implement audit, cleanup and reconciliation worker | Audit/metrics/traces + TTL/orphan attempt cleanup | MCP Server v1.1 | MCP-004; INT-005 | Budget/attempt recovery observable; no protected data in audit metadata. | OUF-E2E-009; OUF-E2E-010; OUF-E2E-011; OUF-E2E-025 | integration; security; resilience | P1 | L | NO | Not Started
MCP-010 | MCP Server | W5 | MCP acceptance | Run MCP-A and canonical E2E acceptance suite | MCP release evidence package | MCP-A; OUF-E2E v0.3 | MCP-005; MCP-006; MCP-007; MCP-008; MCP-009; INT-010 | MCP-A including A53..55 green; canonical scenarios 008..016/021..025 green where applicable. | OUF-E2E-009; OUF-E2E-010; OUF-E2E-011; OUF-E2E-012; OUF-E2E-016 | e2e; performance; acceptance | P0 | XL | YES | Not Started
THS-001 | Onboarding & THS | W2 | Protected Operations | Implement protected-log typed query service | ProtectedLogQueryService search/read/filter | THS PET v1.4+ | ONB-001; AUTH-005 | HUMAN_USER only; typed filters; no arbitrary query language; server-side caps. | OUF-E2E-016 | integration; security | P0 | L | YES | Not Started
THS-002 | Onboarding & THS | W2 | Protected Operations | Implement authorization/redaction guard | ProtectedLogAuthorizationGuard + RedactionService | Authorization SDK; THS PET | THS-001; AUTH-006 | Permission/resource/purpose/assurance checked before serialization; secret/token/cookie always removed. | OUF-E2E-016 | integration; security | P0 | L | YES | Not Started
THS-003 | Onboarding & THS | W2 | Protected Operations | Implement deterministic aggregate/correlate | ProtectedLogAggregationService | THS PET | THS-002 | Only predefined dimensions/keys; disclosure controls; no AI inference. | OUF-E2E-016 | integration; performance | P1 | M | NO | Not Started
THS-004 | Onboarding & THS | W2 | Protected Operations | Implement governed async export/download | ProtectedLogExportService + manifest/checksum/expiry | THS PET | THS-002 | Fresh auth, purpose/reason, result cap, one-time/short-lived download reference, full audit. | OUF-E2E-016 | integration; security | P1 | L | NO | Not Started
THS-005 | Onboarding & THS | W3 | Protected Operations | Implement Trusted UI Shell route/session controls for protected workspace | HUMAN_USER browser session, CSRF/CSP/cookie/step-up controls | THS PET; IAM bindings | THS-001; THS-002; INT-004 | Protected workspace accessible only via THS/Gateway human path; no MCP binding. | OUF-E2E-016 | security; e2e | P0 | L | YES | Not Started
THS-006 | Onboarding & THS | W4 | Protected Operations | Run THS-A protected-log acceptance suite | THS-A12 + protected-operation isolation evidence | THS-A; MCP-A53..55 | THS-003; THS-004; THS-005; MCP-008 | search/read/filter/aggregate/correlate/export/download all remain inside THS; no payload to MCP. | OUF-E2E-016 | e2e; security; acceptance | P0 | L | YES | Not Started
ING-013 | Ingestion Runtime | W3 | Snapshot change detection | Close unchanged FULL_SNAPSHOT no-op path | Executable no-change snapshot contract/integration test and UDP handoff evidence | Ingestion v1.2 change detection; HandoffPayload; LineageRecord | ING-004; ING-007; UDP-004 | Unchanged FULL_SNAPSHOT produces coherent run/handoff/lineage evidence and no unnecessary Canonical Revision in UDP. | OUF-E2E-003 | contract; integration; e2e | P0 | M | YES | Not Started
ONB-015 | Onboarding & THS | W3 | WFS onboarding vertical slice | Close conversational WFS onboarding vertical slice | URL→discovery→mapping/CRS/identity/temporality→THS approval→bundle→first ingestion evidence | PublishedConfigurationBundle; SemanticReference; SourceObjectIdentityPolicy; TemporalMapping; THS boundary | ONB-003; ONB-005; ONB-009; GW-004; SEM-003; ING-003 | OUF-E2E-005 driver passes with exact refs and direct HUMAN_USER approval path; no MCP confirm. | OUF-E2E-005 | integration; security; e2e | P0 | L | YES | Not Started
UDP-015 | UDP / Urban Object Registry | W3 | Multi-source resolution vertical slice | Close two-source same Urban Object vertical slice | Deterministic candidate→MATCH test with one UrbanObjectId, multiple SourceBindings and property authority evidence | SourceObjectIdentityPolicy; LineageRecord; AuthorityPolicyDescriptor; UDP resolution rules | UDP-005; UDP-006; ONB-006; ING-007 | OUF-E2E-006 driver passes and proves sourceObjectId≠UrbanObjectId plus explainable per-property provenance/authority. | OUF-E2E-006; OUF-E2E-020 | integration; e2e | P0 | L | YES | Not Started

## Dependencies
Successor | Successor Team | Successor Wave | Predecessor | Predecessor Team | Predecessor Wave | Order Check
INT-002 | Integration & QA | W0 | INT-001 | Integration & QA | W0 | OK
INT-003 | Integration & QA | W0 | INT-002 | Integration & QA | W0 | OK
INT-004 | Integration & QA | W0 | INT-001 | Integration & QA | W0 | OK
INT-005 | Integration & QA | W0 | INT-002 | Integration & QA | W0 | OK
INT-006 | Integration & QA | W1 | INT-004 | Integration & QA | W0 | OK
INT-007 | Integration & QA | W1 | INT-001 | Integration & QA | W0 | OK
INT-007 | Integration & QA | W1 | INT-002 | Integration & QA | W0 | OK
INT-008 | Integration & QA | W2 | INT-007 | Integration & QA | W1 | OK
INT-009 | Integration & QA | W3 | INT-007 | Integration & QA | W1 | OK
INT-009 | Integration & QA | W3 | INT-008 | Integration & QA | W2 | OK
INT-010 | Integration & QA | W4 | INT-009 | Integration & QA | W3 | OK
INT-011 | Integration & QA | W5 | INT-009 | Integration & QA | W3 | OK
INT-012 | Integration & QA | W5 | INT-011 | Integration & QA | W5 | OK
AUTH-001 | Authorization | W0 | INT-002 | Integration & QA | W0 | OK
AUTH-001 | Authorization | W0 | INT-003 | Integration & QA | W0 | OK
AUTH-002 | Authorization | W1 | AUTH-001 | Authorization | W0 | OK
AUTH-002 | Authorization | W1 | INT-006 | Integration & QA | W1 | OK
AUTH-003 | Authorization | W1 | AUTH-001 | Authorization | W0 | OK
AUTH-003 | Authorization | W1 | INT-007 | Integration & QA | W1 | OK
AUTH-004 | Authorization | W1 | AUTH-001 | Authorization | W0 | OK
AUTH-005 | Authorization | W2 | AUTH-002 | Authorization | W1 | OK
AUTH-005 | Authorization | W2 | AUTH-003 | Authorization | W1 | OK
AUTH-005 | Authorization | W2 | AUTH-004 | Authorization | W1 | OK
AUTH-006 | Authorization | W2 | AUTH-005 | Authorization | W2 | OK
AUTH-007 | Authorization | W2 | AUTH-004 | Authorization | W1 | OK
AUTH-007 | Authorization | W2 | AUTH-005 | Authorization | W2 | OK
AUTH-008 | Authorization | W2 | AUTH-005 | Authorization | W2 | OK
AUTH-009 | Authorization | W3 | AUTH-005 | Authorization | W2 | OK
AUTH-010 | Authorization | W3 | AUTH-006 | Authorization | W2 | OK
AUTH-011 | Authorization | W4 | AUTH-005 | Authorization | W2 | OK
AUTH-011 | Authorization | W4 | AUTH-007 | Authorization | W2 | OK
AUTH-012 | Authorization | W5 | AUTH-011 | Authorization | W4 | OK
AUTH-012 | Authorization | W5 | INT-010 | Integration & QA | W4 | OK
GW-001 | Urban API Gateway | W0 | INT-002 | Integration & QA | W0 | OK
GW-001 | Urban API Gateway | W0 | INT-003 | Integration & QA | W0 | OK
GW-002 | Urban API Gateway | W1 | GW-001 | Urban API Gateway | W0 | OK
GW-002 | Urban API Gateway | W1 | INT-006 | Integration & QA | W1 | OK
GW-002 | Urban API Gateway | W1 | AUTH-002 | Authorization | W1 | OK
GW-003 | Urban API Gateway | W1 | GW-001 | Urban API Gateway | W0 | OK
GW-003 | Urban API Gateway | W1 | AUTH-003 | Authorization | W1 | OK
GW-004 | Urban API Gateway | W2 | GW-001 | Urban API Gateway | W0 | OK
GW-004 | Urban API Gateway | W2 | ONB-008 | Onboarding & THS | W2 | OK
GW-005 | Urban API Gateway | W2 | GW-002 | Urban API Gateway | W1 | OK
GW-005 | Urban API Gateway | W2 | GW-003 | Urban API Gateway | W1 | OK
GW-006 | Urban API Gateway | W2 | GW-004 | Urban API Gateway | W2 | OK
GW-007 | Urban API Gateway | W2 | GW-004 | Urban API Gateway | W2 | OK
GW-007 | Urban API Gateway | W2 | GW-005 | Urban API Gateway | W2 | OK
GW-008 | Urban API Gateway | W2 | INT-005 | Integration & QA | W0 | OK
GW-008 | Urban API Gateway | W2 | GW-005 | Urban API Gateway | W2 | OK
GW-009 | Urban API Gateway | W3 | GW-005 | Urban API Gateway | W2 | OK
GW-010 | Urban API Gateway | W3 | GW-004 | Urban API Gateway | W2 | OK
GW-010 | Urban API Gateway | W3 | GW-008 | Urban API Gateway | W2 | OK
GW-011 | Urban API Gateway | W3 | GW-003 | Urban API Gateway | W1 | OK
GW-011 | Urban API Gateway | W3 | GW-004 | Urban API Gateway | W2 | OK
GW-012 | Urban API Gateway | W4 | GW-002 | Urban API Gateway | W1 | OK
GW-012 | Urban API Gateway | W4 | AUTH-007 | Authorization | W2 | OK
GW-013 | Urban API Gateway | W5 | GW-006 | Urban API Gateway | W2 | OK
GW-013 | Urban API Gateway | W5 | GW-007 | Urban API Gateway | W2 | OK
GW-013 | Urban API Gateway | W5 | GW-008 | Urban API Gateway | W2 | OK
GW-013 | Urban API Gateway | W5 | GW-010 | Urban API Gateway | W3 | OK
GW-013 | Urban API Gateway | W5 | GW-011 | Urban API Gateway | W3 | OK
GW-013 | Urban API Gateway | W5 | GW-012 | Urban API Gateway | W4 | OK
GW-013 | Urban API Gateway | W5 | INT-010 | Integration & QA | W4 | OK
ONB-001 | Onboarding & THS | W0 | INT-002 | Integration & QA | W0 | OK
ONB-001 | Onboarding & THS | W0 | INT-003 | Integration & QA | W0 | OK
ONB-002 | Onboarding & THS | W1 | ONB-001 | Onboarding & THS | W0 | OK
ONB-003 | Onboarding & THS | W1 | ONB-002 | Onboarding & THS | W1 | OK
ONB-004 | Onboarding & THS | W1 | ONB-002 | Onboarding & THS | W1 | OK
ONB-005 | Onboarding & THS | W2 | ONB-002 | Onboarding & THS | W1 | OK
ONB-005 | Onboarding & THS | W2 | SEM-004 | Semantic Registry | W1 | OK
ONB-006 | Onboarding & THS | W2 | ONB-002 | Onboarding & THS | W1 | OK
ONB-006 | Onboarding & THS | W2 | AUTH-003 | Authorization | W1 | OK
ONB-007 | Onboarding & THS | W2 | ONB-003 | Onboarding & THS | W1 | OK
ONB-007 | Onboarding & THS | W2 | ONB-004 | Onboarding & THS | W1 | OK
ONB-007 | Onboarding & THS | W2 | ONB-005 | Onboarding & THS | W2 | OK
ONB-007 | Onboarding & THS | W2 | ONB-006 | Onboarding & THS | W2 | OK
ONB-008 | Onboarding & THS | W2 | ONB-007 | Onboarding & THS | W2 | OK
ONB-009 | Onboarding & THS | W3 | ONB-001 | Onboarding & THS | W0 | OK
ONB-009 | Onboarding & THS | W3 | AUTH-009 | Authorization | W3 | OK
ONB-010 | Onboarding & THS | W3 | ONB-009 | Onboarding & THS | W3 | OK
ONB-011 | Onboarding & THS | W3 | ONB-003 | Onboarding & THS | W1 | OK
ONB-011 | Onboarding & THS | W3 | GW-010 | Urban API Gateway | W3 | OK
ONB-012 | Onboarding & THS | W3 | ONB-004 | Onboarding & THS | W1 | OK
ONB-012 | Onboarding & THS | W3 | ONB-007 | Onboarding & THS | W2 | OK
ONB-013 | Onboarding & THS | W4 | ONB-007 | Onboarding & THS | W2 | OK
ONB-014 | Onboarding & THS | W5 | ONB-010 | Onboarding & THS | W3 | OK
ONB-014 | Onboarding & THS | W5 | ONB-011 | Onboarding & THS | W3 | OK
ONB-014 | Onboarding & THS | W5 | ONB-012 | Onboarding & THS | W3 | OK
ONB-014 | Onboarding & THS | W5 | ONB-013 | Onboarding & THS | W4 | OK
ONB-014 | Onboarding & THS | W5 | INT-010 | Integration & QA | W4 | OK
SEM-001 | Semantic Registry | W0 | INT-002 | Integration & QA | W0 | OK
SEM-001 | Semantic Registry | W0 | INT-003 | Integration & QA | W0 | OK
SEM-002 | Semantic Registry | W1 | SEM-001 | Semantic Registry | W0 | OK
SEM-003 | Semantic Registry | W1 | SEM-002 | Semantic Registry | W1 | OK
SEM-004 | Semantic Registry | W1 | SEM-002 | Semantic Registry | W1 | OK
SEM-005 | Semantic Registry | W2 | SEM-003 | Semantic Registry | W1 | OK
SEM-006 | Semantic Registry | W2 | SEM-005 | Semantic Registry | W2 | OK
SEM-007 | Semantic Registry | W2 | SEM-002 | Semantic Registry | W1 | OK
SEM-007 | Semantic Registry | W2 | SEM-004 | Semantic Registry | W1 | OK
SEM-008 | Semantic Registry | W3 | SEM-007 | Semantic Registry | W2 | OK
SEM-009 | Semantic Registry | W4 | AUTH-011 | Authorization | W4 | OK
SEM-009 | Semantic Registry | W4 | SEM-003 | Semantic Registry | W1 | OK
SEM-010 | Semantic Registry | W5 | SEM-004 | Semantic Registry | W1 | OK
SEM-010 | Semantic Registry | W5 | SEM-007 | Semantic Registry | W2 | OK
SEM-010 | Semantic Registry | W5 | SEM-008 | Semantic Registry | W3 | OK
SEM-010 | Semantic Registry | W5 | SEM-009 | Semantic Registry | W4 | OK
SEM-010 | Semantic Registry | W5 | INT-010 | Integration & QA | W4 | OK
ING-001 | Ingestion Runtime | W0 | INT-002 | Integration & QA | W0 | OK
ING-001 | Ingestion Runtime | W0 | INT-003 | Integration & QA | W0 | OK
ING-002 | Ingestion Runtime | W2 | ING-001 | Ingestion Runtime | W0 | OK
ING-002 | Ingestion Runtime | W2 | ONB-007 | Onboarding & THS | W2 | OK
ING-002 | Ingestion Runtime | W2 | SEM-004 | Semantic Registry | W1 | OK
ING-003 | Ingestion Runtime | W2 | ING-001 | Ingestion Runtime | W0 | OK
ING-003 | Ingestion Runtime | W2 | GW-007 | Urban API Gateway | W2 | OK
ING-004 | Ingestion Runtime | W2 | ING-002 | Ingestion Runtime | W2 | OK
ING-004 | Ingestion Runtime | W2 | ONB-003 | Onboarding & THS | W1 | OK
ING-005 | Ingestion Runtime | W3 | ING-003 | Ingestion Runtime | W2 | OK
ING-005 | Ingestion Runtime | W3 | ONB-012 | Onboarding & THS | W3 | OK
ING-006 | Ingestion Runtime | W2 | ING-004 | Ingestion Runtime | W2 | OK
ING-006 | Ingestion Runtime | W2 | ING-003 | Ingestion Runtime | W2 | OK
ING-007 | Ingestion Runtime | W2 | ING-002 | Ingestion Runtime | W2 | OK
ING-007 | Ingestion Runtime | W2 | ING-003 | Ingestion Runtime | W2 | OK
ING-008 | Ingestion Runtime | W3 | ING-004 | Ingestion Runtime | W2 | OK
ING-008 | Ingestion Runtime | W3 | ING-006 | Ingestion Runtime | W2 | OK
ING-009 | Ingestion Runtime | W3 | GW-010 | Urban API Gateway | W3 | OK
ING-009 | Ingestion Runtime | W3 | ONB-011 | Onboarding & THS | W3 | OK
ING-010 | Ingestion Runtime | W4 | ING-007 | Ingestion Runtime | W2 | OK
ING-010 | Ingestion Runtime | W4 | ONB-013 | Onboarding & THS | W4 | OK
ING-010 | Ingestion Runtime | W4 | SEM-004 | Semantic Registry | W1 | OK
ING-011 | Ingestion Runtime | W4 | AUTH-002 | Authorization | W1 | OK
ING-011 | Ingestion Runtime | W4 | INT-005 | Integration & QA | W0 | OK
ING-012 | Ingestion Runtime | W5 | ING-005 | Ingestion Runtime | W3 | OK
ING-012 | Ingestion Runtime | W5 | ING-006 | Ingestion Runtime | W2 | OK
ING-012 | Ingestion Runtime | W5 | ING-009 | Ingestion Runtime | W3 | OK
ING-012 | Ingestion Runtime | W5 | ING-010 | Ingestion Runtime | W4 | OK
ING-012 | Ingestion Runtime | W5 | ING-011 | Ingestion Runtime | W4 | OK
ING-012 | Ingestion Runtime | W5 | INT-010 | Integration & QA | W4 | OK
UDP-001 | UDP / Urban Object Registry | W0 | INT-002 | Integration & QA | W0 | OK
UDP-001 | UDP / Urban Object Registry | W0 | INT-003 | Integration & QA | W0 | OK
UDP-002 | UDP / Urban Object Registry | W1 | UDP-001 | UDP / Urban Object Registry | W0 | OK
UDP-003 | UDP / Urban Object Registry | W2 | UDP-001 | UDP / Urban Object Registry | W0 | OK
UDP-003 | UDP / Urban Object Registry | W2 | ING-006 | Ingestion Runtime | W2 | OK
UDP-004 | UDP / Urban Object Registry | W3 | UDP-002 | UDP / Urban Object Registry | W1 | OK
UDP-004 | UDP / Urban Object Registry | W3 | UDP-003 | UDP / Urban Object Registry | W2 | OK
UDP-004 | UDP / Urban Object Registry | W3 | ING-005 | Ingestion Runtime | W3 | OK
UDP-005 | UDP / Urban Object Registry | W2 | UDP-002 | UDP / Urban Object Registry | W1 | OK
UDP-005 | UDP / Urban Object Registry | W2 | ING-007 | Ingestion Runtime | W2 | OK
UDP-006 | UDP / Urban Object Registry | W2 | UDP-002 | UDP / Urban Object Registry | W1 | OK
UDP-006 | UDP / Urban Object Registry | W2 | UDP-005 | UDP / Urban Object Registry | W2 | OK
UDP-007 | UDP / Urban Object Registry | W3 | UDP-004 | UDP / Urban Object Registry | W3 | OK
UDP-007 | UDP / Urban Object Registry | W3 | UDP-006 | UDP / Urban Object Registry | W2 | OK
UDP-007 | UDP / Urban Object Registry | W3 | SEM-004 | Semantic Registry | W1 | OK
UDP-008 | UDP / Urban Object Registry | W4 | AUTH-011 | Authorization | W4 | OK
UDP-008 | UDP / Urban Object Registry | W4 | UDP-002 | UDP / Urban Object Registry | W1 | OK
UDP-009 | UDP / Urban Object Registry | W4 | UDP-002 | UDP / Urban Object Registry | W1 | OK
UDP-009 | UDP / Urban Object Registry | W4 | UDP-007 | UDP / Urban Object Registry | W3 | OK
UDP-009 | UDP / Urban Object Registry | W4 | UDP-008 | UDP / Urban Object Registry | W4 | OK
UDP-010 | UDP / Urban Object Registry | W4 | UDP-009 | UDP / Urban Object Registry | W4 | OK
UDP-011 | UDP / Urban Object Registry | W4 | UDP-008 | UDP / Urban Object Registry | W4 | OK
UDP-011 | UDP / Urban Object Registry | W4 | UDP-009 | UDP / Urban Object Registry | W4 | OK
UDP-012 | UDP / Urban Object Registry | W4 | UDP-005 | UDP / Urban Object Registry | W2 | OK
UDP-012 | UDP / Urban Object Registry | W4 | ING-010 | Ingestion Runtime | W4 | OK
UDP-013 | UDP / Urban Object Registry | W4 | UDP-003 | UDP / Urban Object Registry | W2 | OK
UDP-013 | UDP / Urban Object Registry | W4 | INT-004 | Integration & QA | W0 | OK
UDP-014 | UDP / Urban Object Registry | W5 | UDP-010 | UDP / Urban Object Registry | W4 | OK
UDP-014 | UDP / Urban Object Registry | W5 | UDP-011 | UDP / Urban Object Registry | W4 | OK
UDP-014 | UDP / Urban Object Registry | W5 | UDP-012 | UDP / Urban Object Registry | W4 | OK
UDP-014 | UDP / Urban Object Registry | W5 | UDP-013 | UDP / Urban Object Registry | W4 | OK
UDP-014 | UDP / Urban Object Registry | W5 | INT-010 | Integration & QA | W4 | OK
MCP-001 | MCP Server | W0 | INT-002 | Integration & QA | W0 | OK
MCP-001 | MCP Server | W0 | INT-003 | Integration & QA | W0 | OK
MCP-002 | MCP Server | W1 | MCP-001 | MCP Server | W0 | OK
MCP-002 | MCP Server | W1 | AUTH-003 | Authorization | W1 | OK
MCP-002 | MCP Server | W1 | GW-003 | Urban API Gateway | W1 | OK
MCP-003 | MCP Server | W2 | MCP-001 | MCP Server | W0 | OK
MCP-003 | MCP Server | W2 | AUTH-005 | Authorization | W2 | OK
MCP-003 | MCP Server | W2 | GW-005 | Urban API Gateway | W2 | OK
MCP-004 | MCP Server | W2 | MCP-001 | MCP Server | W0 | OK
MCP-005 | MCP Server | W2 | MCP-002 | MCP Server | W1 | OK
MCP-005 | MCP Server | W2 | MCP-004 | MCP Server | W2 | OK
MCP-006 | MCP Server | W2 | MCP-002 | MCP Server | W1 | OK
MCP-006 | MCP Server | W2 | MCP-003 | MCP Server | W2 | OK
MCP-006 | MCP Server | W2 | GW-008 | Urban API Gateway | W2 | OK
MCP-007 | MCP Server | W3 | MCP-003 | MCP Server | W2 | OK
MCP-007 | MCP Server | W3 | ONB-010 | Onboarding & THS | W3 | OK
MCP-008 | MCP Server | W4 | MCP-002 | MCP Server | W1 | OK
MCP-008 | MCP Server | W4 | THS-001 | Onboarding & THS | W2 | OK
MCP-008 | MCP Server | W4 | THS-002 | Onboarding & THS | W2 | OK
MCP-008 | MCP Server | W4 | THS-005 | Onboarding & THS | W3 | OK
MCP-009 | MCP Server | W4 | MCP-004 | MCP Server | W2 | OK
MCP-009 | MCP Server | W4 | INT-005 | Integration & QA | W0 | OK
MCP-010 | MCP Server | W5 | MCP-005 | MCP Server | W2 | OK
MCP-010 | MCP Server | W5 | MCP-006 | MCP Server | W2 | OK
MCP-010 | MCP Server | W5 | MCP-007 | MCP Server | W3 | OK
MCP-010 | MCP Server | W5 | MCP-008 | MCP Server | W4 | OK
MCP-010 | MCP Server | W5 | MCP-009 | MCP Server | W4 | OK
MCP-010 | MCP Server | W5 | INT-010 | Integration & QA | W4 | OK
THS-001 | Onboarding & THS | W2 | ONB-001 | Onboarding & THS | W0 | OK
THS-001 | Onboarding & THS | W2 | AUTH-005 | Authorization | W2 | OK
THS-002 | Onboarding & THS | W2 | THS-001 | Onboarding & THS | W2 | OK
THS-002 | Onboarding & THS | W2 | AUTH-006 | Authorization | W2 | OK
THS-003 | Onboarding & THS | W2 | THS-002 | Onboarding & THS | W2 | OK
THS-004 | Onboarding & THS | W2 | THS-002 | Onboarding & THS | W2 | OK
THS-005 | Onboarding & THS | W3 | THS-001 | Onboarding & THS | W2 | OK
THS-005 | Onboarding & THS | W3 | THS-002 | Onboarding & THS | W2 | OK
THS-005 | Onboarding & THS | W3 | INT-004 | Integration & QA | W0 | OK
THS-006 | Onboarding & THS | W4 | THS-003 | Onboarding & THS | W2 | OK
THS-006 | Onboarding & THS | W4 | THS-004 | Onboarding & THS | W2 | OK
THS-006 | Onboarding & THS | W4 | THS-005 | Onboarding & THS | W3 | OK
THS-006 | Onboarding & THS | W4 | MCP-008 | MCP Server | W4 | OK
ING-013 | Ingestion Runtime | W3 | ING-004 | Ingestion Runtime | W2 | OK
ING-013 | Ingestion Runtime | W3 | ING-007 | Ingestion Runtime | W2 | OK
ING-013 | Ingestion Runtime | W3 | UDP-004 | UDP / Urban Object Registry | W3 | OK
ONB-015 | Onboarding & THS | W3 | ONB-003 | Onboarding & THS | W1 | OK
ONB-015 | Onboarding & THS | W3 | ONB-005 | Onboarding & THS | W2 | OK
ONB-015 | Onboarding & THS | W3 | ONB-009 | Onboarding & THS | W3 | OK
ONB-015 | Onboarding & THS | W3 | GW-004 | Urban API Gateway | W2 | OK
ONB-015 | Onboarding & THS | W3 | SEM-003 | Semantic Registry | W1 | OK
ONB-015 | Onboarding & THS | W3 | ING-003 | Ingestion Runtime | W2 | OK
UDP-015 | UDP / Urban Object Registry | W3 | UDP-005 | UDP / Urban Object Registry | W2 | OK
UDP-015 | UDP / Urban Object Registry | W3 | UDP-006 | UDP / Urban Object Registry | W2 | OK
UDP-015 | UDP / Urban Object Registry | W3 | ONB-006 | Onboarding & THS | W2 | OK
UDP-015 | UDP / Urban Object Registry | W3 | ING-007 | Ingestion Runtime | W2 | OK

## E2E Coverage
Scenario | Title | Lead Team | Evidence Owner | Participating Modules | Explicit WBS Tasks | Status
OUF-E2E-001 | Schema drift breaking | Onboarding & THS | Integration & QA | Gateway, Ingestion, Onboarding | GW-010; ONB-011; ONB-013; ONB-014; ING-009; ING-012; INT-010 | Not Started
OUF-E2E-002 | Durable ACK failure | Ingestion Runtime | Integration & QA | Gateway, Ingestion, UDP | GW-007; ING-006; ING-008; ING-012; UDP-003; UDP-014; INT-010 | Not Started
OUF-E2E-003 | Full snapshot unchanged | Ingestion Runtime | Integration & QA | Ingestion, UDP | ING-004; ING-005; ING-013; UDP-004; UDP-014 | Not Started
OUF-E2E-004 | Delta patch deterministic recovery | Ingestion Runtime | Integration & QA | Onboarding, Ingestion, UDP | ONB-012; ING-005; ING-006; ING-008; ING-012; UDP-004; UDP-014 | Not Started
OUF-E2E-005 | Conversational WFS onboarding | Onboarding & THS | Integration & QA | MCP, Gateway, Onboarding, Semantic Registry, THS, Ingestion, UDP | MCP-006; MCP-007; GW-004; GW-006; ONB-003; ONB-005; ONB-007; ONB-008; ONB-009; ONB-010; ONB-015; SEM-003; SEM-004; ING-002; ING-003; UDP-004 | Not Started
OUF-E2E-006 | Multi-source same Urban Object | UDP / Urban Object Registry | Integration & QA | Onboarding, Ingestion, UDP | ONB-004; ONB-006; ING-007; UDP-002; UDP-005; UDP-006; UDP-015 | Not Started
OUF-E2E-007 | Future personal-data inclusion | Authorization | Integration & QA | Onboarding, Authorization, UDP, MCP | ONB-006; ONB-007; AUTH-005; AUTH-006; AUTH-008; AUTH-011; UDP-008; UDP-011; MCP-003; MCP-006 | Not Started
OUF-E2E-008 | Wrong graph tool remediation | MCP Server | Integration & QA | MCP, Gateway, UDP | MCP-002; MCP-005; MCP-006; GW-003; UDP-009; UDP-010 | Not Started
OUF-E2E-009 | Aggressive equivalent retry guard | MCP Server | Integration & QA | MCP | MCP-004; MCP-005; MCP-009; MCP-010 | Not Started
OUF-E2E-010 | Multi-Pod MCP cumulative budget | MCP Server | Integration & QA | MCP | MCP-004; MCP-009; MCP-010 | Not Started
OUF-E2E-011 | Budget contention and pool protection | MCP Server | Integration & QA | MCP | MCP-004; MCP-009; MCP-010 | Not Started
OUF-E2E-012 | Adaptive exploration | MCP Server | Integration & QA | MCP, UDP | MCP-004; MCP-006; MCP-010; UDP-009; UDP-010 | Not Started
OUF-E2E-013 | Analytical boundary | MCP Server | Integration & QA | MCP, Gateway, UDP | MCP-002; MCP-005; MCP-006; GW-003; GW-005; UDP-009; UDP-010 | Not Started
OUF-E2E-014 | Human merge | Onboarding & THS | Integration & QA | MCP, Gateway, THS, Authorization, UDP | MCP-003; MCP-007; GW-012; ONB-009; ONB-010; AUTH-009; AUTH-011; UDP-006; UDP-008; UDP-014 | Not Started
OUF-E2E-015 | Historical replay | Ingestion Runtime | Integration & QA | Ingestion, Onboarding, Semantic Registry, UDP, Authorization | ING-007; ING-010; ING-012; ONB-013; SEM-003; SEM-004; SEM-010; UDP-012; UDP-014; AUTH-005 | Not Started
OUF-E2E-016 | Protected logs boundary | Onboarding & THS | Integration & QA | MCP, Gateway, THS, Authorization | MCP-008; MCP-010; THS-001; THS-002; THS-003; THS-004; THS-005; THS-006; AUTH-005; AUTH-006; AUTH-008; AUTH-009; GW-002; GW-005; GW-008; GW-012; INT-005 | Not Started
OUF-E2E-017 | Source configuration activation to first successful ingestion | Integration & QA | Integration & QA | Onboarding, Gateway, Ingestion, UDP | ONB-007; ONB-008; GW-004; GW-007; ING-002; ING-003; ING-006; ING-007; UDP-003; UDP-004; INT-009 | Not Started
OUF-E2E-018 | Authorization coarse allow with backend fine-grained deny | Authorization | Integration & QA | Gateway, Authorization, UDP | GW-005; GW-008; GW-012; AUTH-005; AUTH-007; AUTH-008; AUTH-011; UDP-008 | Not Started
OUF-E2E-019 | Semantic publication pin remains stable during ingestion | Semantic Registry | Integration & QA | Semantic Registry, Onboarding, Ingestion, UDP | SEM-004; SEM-010; ONB-005; ONB-007; ING-002; ING-007; UDP-005; UDP-012 | Not Started
OUF-E2E-020 | Source-object identity never becomes UrbanObjectId | UDP / Urban Object Registry | Integration & QA | Onboarding, Ingestion, UDP | ONB-004; ING-003; ING-007; UDP-002; UDP-005; UDP-006; UDP-015 | Not Started
OUF-E2E-021 | Scenario-neutral M2M identity across two provider profiles | Integration & QA | Integration & QA | Gateway, Authorization, MCP/Backend | INT-004; INT-006; AUTH-002; AUTH-009; GW-002; GW-012; MCP-003 | Not Started
OUF-E2E-022 | MCP capability projection consistency | Integration & QA | Integration & QA | MCP, Gateway, Authorization | MCP-002; MCP-003; GW-003; GW-005; AUTH-003; AUTH-005; INT-007 | Not Started
OUF-E2E-023 | Southbound egress bypass is blocked | Urban API Gateway | Integration & QA | Gateway, Ingestion, MCP, Platform Network | GW-006; GW-013; ING-011; MCP-003; MCP-006; INT-004; INT-010 | Not Started
OUF-E2E-024 | Gateway controlled publication retains last-known-good | Urban API Gateway | Integration & QA | Gateway, Onboarding, Operations | GW-004; GW-011; GW-013; ONB-008; INT-010 | Not Started
OUF-E2E-025 | ProblemDetails and correlation preservation across full path | Integration & QA | Integration & QA | MCP, Gateway, Backend Owner, Ingestion/UDP | INT-005; INT-009; GW-008; GW-012; MCP-006; MCP-009; ING-007; ING-011; UDP-005; AUTH-008 | Not Started

## Milestones
Milestone | Name | Wave | Exit
M0 | Baseline adopted | W0 | Contracts rc3 + Starter v0.2 + canonical E2E namespace pinned
M1 | Security spine | W1 | Scenario-neutral identity + Authorization + Gateway + MCP context path green
M2 | Runtime publication | W2 | Onboarding bundle + Semantic publication + Gateway publication ready
M3 | First vertical slice | W3 | OUF-E2E-017 green; durable path progressing
M4 | Governance & protected operations | W4 | OUF-E2E-014/016 plus replay/query hardening green
M5 | Acceptance candidate | W5 | 25 canonical E2E traceability complete; module suites and evidence package complete

## Risks & Gates
ID | Gate | Status | Current rule
PLAT-01 | IAM/M2M scenario A/B/C | OPEN EXTERNAL | Does not block contract/integration mocks; required for representative acceptance/production binding
PLAT-02 | Actual issuer/JWKS/audiences/claims | OPEN EXTERNAL | Mock/provider-neutral integration allowed; real values required for acceptance
PLAT-03 | Service identity lifecycle | OPEN EXTERNAL | Synthetic/service-account integration allowed; production lifecycle required before release
PLAT-04 | Environment routes/endpoints | OPEN EXTERNAL | Stub/service-ref integration allowed
PLAT-05 | Secrets/PKI | OPEN EXTERNAL | References only until platform binding
PLAT-06 | DB/object/log bindings | OPEN EXTERNAL | Testcontainers/local compatible services allowed
PLAT-07 | RPO/RTO/backup | OPEN EXTERNAL | Does not block functional coding; required for ops acceptance
PLAT-08 | Representative acceptance environment | OPEN EXTERNAL | Required only for final production acceptance layer

## v0.3 Changes
Re-audit finding | v0.3 remediation | Status
RA-01 | MCP-008 now depends on THS implementation tasks; THS-006 remains downstream joint acceptance | CLOSED
RA-02 | E2E v0.3 contains scenario-specific executable definitions for all 25 canonical scenarios | CLOSED
RA-03 | Added ING-013 / ONB-015 / UDP-015 plus explicit WBS linkage for 003/005/006 | CLOSED
RA-04 | Starter Kit v0.2.1 pins current rc3-coherence baseline consistently | CLOSED
RA-05 | All task references are explicit canonical IDs; normalized WBS-E2E Map and Lead/Evidence Owner added | CLOSED
RA-06 | Readiness status will be republished after final validation | CLOSED BY READINESS v1.2

## WBS-E2E Map
WBS ID | Task Team | Wave | Scenario | Scenario Lead | Evidence Owner
GW-010 | Urban API Gateway | W3 | OUF-E2E-001 | Onboarding & THS | Integration & QA
ONB-011 | Onboarding & THS | W3 | OUF-E2E-001 | Onboarding & THS | Integration & QA
ONB-013 | Onboarding & THS | W4 | OUF-E2E-001 | Onboarding & THS | Integration & QA
ONB-014 | Onboarding & THS | W5 | OUF-E2E-001 | Onboarding & THS | Integration & QA
ING-009 | Ingestion Runtime | W3 | OUF-E2E-001 | Onboarding & THS | Integration & QA
ING-012 | Ingestion Runtime | W5 | OUF-E2E-001 | Onboarding & THS | Integration & QA
INT-010 | Integration & QA | W4 | OUF-E2E-001 | Onboarding & THS | Integration & QA
GW-007 | Urban API Gateway | W2 | OUF-E2E-002 | Ingestion Runtime | Integration & QA
ING-006 | Ingestion Runtime | W2 | OUF-E2E-002 | Ingestion Runtime | Integration & QA
ING-008 | Ingestion Runtime | W3 | OUF-E2E-002 | Ingestion Runtime | Integration & QA
ING-012 | Ingestion Runtime | W5 | OUF-E2E-002 | Ingestion Runtime | Integration & QA
UDP-003 | UDP / Urban Object Registry | W2 | OUF-E2E-002 | Ingestion Runtime | Integration & QA
UDP-014 | UDP / Urban Object Registry | W5 | OUF-E2E-002 | Ingestion Runtime | Integration & QA
INT-010 | Integration & QA | W4 | OUF-E2E-002 | Ingestion Runtime | Integration & QA
ING-004 | Ingestion Runtime | W2 | OUF-E2E-003 | Ingestion Runtime | Integration & QA
ING-005 | Ingestion Runtime | W3 | OUF-E2E-003 | Ingestion Runtime | Integration & QA
ING-013 | Ingestion Runtime | W3 | OUF-E2E-003 | Ingestion Runtime | Integration & QA
UDP-004 | UDP / Urban Object Registry | W3 | OUF-E2E-003 | Ingestion Runtime | Integration & QA
UDP-014 | UDP / Urban Object Registry | W5 | OUF-E2E-003 | Ingestion Runtime | Integration & QA
ONB-012 | Onboarding & THS | W3 | OUF-E2E-004 | Ingestion Runtime | Integration & QA
ING-005 | Ingestion Runtime | W3 | OUF-E2E-004 | Ingestion Runtime | Integration & QA
ING-006 | Ingestion Runtime | W2 | OUF-E2E-004 | Ingestion Runtime | Integration & QA
ING-008 | Ingestion Runtime | W3 | OUF-E2E-004 | Ingestion Runtime | Integration & QA
ING-012 | Ingestion Runtime | W5 | OUF-E2E-004 | Ingestion Runtime | Integration & QA
UDP-004 | UDP / Urban Object Registry | W3 | OUF-E2E-004 | Ingestion Runtime | Integration & QA
UDP-014 | UDP / Urban Object Registry | W5 | OUF-E2E-004 | Ingestion Runtime | Integration & QA
MCP-006 | MCP Server | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
MCP-007 | MCP Server | W3 | OUF-E2E-005 | Onboarding & THS | Integration & QA
GW-004 | Urban API Gateway | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
GW-006 | Urban API Gateway | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-003 | Onboarding & THS | W1 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-005 | Onboarding & THS | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-007 | Onboarding & THS | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-008 | Onboarding & THS | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-009 | Onboarding & THS | W3 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-010 | Onboarding & THS | W3 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-015 | Onboarding & THS | W3 | OUF-E2E-005 | Onboarding & THS | Integration & QA
SEM-003 | Semantic Registry | W1 | OUF-E2E-005 | Onboarding & THS | Integration & QA
SEM-004 | Semantic Registry | W1 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ING-002 | Ingestion Runtime | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ING-003 | Ingestion Runtime | W2 | OUF-E2E-005 | Onboarding & THS | Integration & QA
UDP-004 | UDP / Urban Object Registry | W3 | OUF-E2E-005 | Onboarding & THS | Integration & QA
ONB-004 | Onboarding & THS | W1 | OUF-E2E-006 | UDP / Urban Object Registry | Integration & QA
ONB-006 | Onboarding & THS | W2 | OUF-E2E-006 | UDP / Urban Object Registry | Integration & QA
ING-007 | Ingestion Runtime | W2 | OUF-E2E-006 | UDP / Urban Object Registry | Integration & QA
UDP-002 | UDP / Urban Object Registry | W1 | OUF-E2E-006 | UDP / Urban Object Registry | Integration & QA
UDP-005 | UDP / Urban Object Registry | W2 | OUF-E2E-006 | UDP / Urban Object Registry | Integration & QA
UDP-006 | UDP / Urban Object Registry | W2 | OUF-E2E-006 | UDP / Urban Object Registry | Integration & QA
UDP-015 | UDP / Urban Object Registry | W3 | OUF-E2E-006 | UDP / Urban Object Registry | Integration & QA
ONB-006 | Onboarding & THS | W2 | OUF-E2E-007 | Authorization | Integration & QA
ONB-007 | Onboarding & THS | W2 | OUF-E2E-007 | Authorization | Integration & QA
AUTH-005 | Authorization | W2 | OUF-E2E-007 | Authorization | Integration & QA
AUTH-006 | Authorization | W2 | OUF-E2E-007 | Authorization | Integration & QA
AUTH-008 | Authorization | W2 | OUF-E2E-007 | Authorization | Integration & QA
AUTH-011 | Authorization | W4 | OUF-E2E-007 | Authorization | Integration & QA
UDP-008 | UDP / Urban Object Registry | W4 | OUF-E2E-007 | Authorization | Integration & QA
UDP-011 | UDP / Urban Object Registry | W4 | OUF-E2E-007 | Authorization | Integration & QA
MCP-003 | MCP Server | W2 | OUF-E2E-007 | Authorization | Integration & QA
MCP-006 | MCP Server | W2 | OUF-E2E-007 | Authorization | Integration & QA
MCP-002 | MCP Server | W1 | OUF-E2E-008 | MCP Server | Integration & QA
MCP-005 | MCP Server | W2 | OUF-E2E-008 | MCP Server | Integration & QA
MCP-006 | MCP Server | W2 | OUF-E2E-008 | MCP Server | Integration & QA
GW-003 | Urban API Gateway | W1 | OUF-E2E-008 | MCP Server | Integration & QA
UDP-009 | UDP / Urban Object Registry | W4 | OUF-E2E-008 | MCP Server | Integration & QA
UDP-010 | UDP / Urban Object Registry | W4 | OUF-E2E-008 | MCP Server | Integration & QA
MCP-004 | MCP Server | W2 | OUF-E2E-009 | MCP Server | Integration & QA
MCP-005 | MCP Server | W2 | OUF-E2E-009 | MCP Server | Integration & QA
MCP-009 | MCP Server | W4 | OUF-E2E-009 | MCP Server | Integration & QA
MCP-010 | MCP Server | W5 | OUF-E2E-009 | MCP Server | Integration & QA
MCP-004 | MCP Server | W2 | OUF-E2E-010 | MCP Server | Integration & QA
MCP-009 | MCP Server | W4 | OUF-E2E-010 | MCP Server | Integration & QA
MCP-010 | MCP Server | W5 | OUF-E2E-010 | MCP Server | Integration & QA
MCP-004 | MCP Server | W2 | OUF-E2E-011 | MCP Server | Integration & QA
MCP-009 | MCP Server | W4 | OUF-E2E-011 | MCP Server | Integration & QA
MCP-010 | MCP Server | W5 | OUF-E2E-011 | MCP Server | Integration & QA
MCP-004 | MCP Server | W2 | OUF-E2E-012 | MCP Server | Integration & QA
MCP-006 | MCP Server | W2 | OUF-E2E-012 | MCP Server | Integration & QA
MCP-010 | MCP Server | W5 | OUF-E2E-012 | MCP Server | Integration & QA
UDP-009 | UDP / Urban Object Registry | W4 | OUF-E2E-012 | MCP Server | Integration & QA
UDP-010 | UDP / Urban Object Registry | W4 | OUF-E2E-012 | MCP Server | Integration & QA
MCP-002 | MCP Server | W1 | OUF-E2E-013 | MCP Server | Integration & QA
MCP-005 | MCP Server | W2 | OUF-E2E-013 | MCP Server | Integration & QA
MCP-006 | MCP Server | W2 | OUF-E2E-013 | MCP Server | Integration & QA
GW-003 | Urban API Gateway | W1 | OUF-E2E-013 | MCP Server | Integration & QA
GW-005 | Urban API Gateway | W2 | OUF-E2E-013 | MCP Server | Integration & QA
UDP-009 | UDP / Urban Object Registry | W4 | OUF-E2E-013 | MCP Server | Integration & QA
UDP-010 | UDP / Urban Object Registry | W4 | OUF-E2E-013 | MCP Server | Integration & QA
MCP-003 | MCP Server | W2 | OUF-E2E-014 | Onboarding & THS | Integration & QA
MCP-007 | MCP Server | W3 | OUF-E2E-014 | Onboarding & THS | Integration & QA
GW-012 | Urban API Gateway | W4 | OUF-E2E-014 | Onboarding & THS | Integration & QA
ONB-009 | Onboarding & THS | W3 | OUF-E2E-014 | Onboarding & THS | Integration & QA
ONB-010 | Onboarding & THS | W3 | OUF-E2E-014 | Onboarding & THS | Integration & QA
AUTH-009 | Authorization | W3 | OUF-E2E-014 | Onboarding & THS | Integration & QA
AUTH-011 | Authorization | W4 | OUF-E2E-014 | Onboarding & THS | Integration & QA
UDP-006 | UDP / Urban Object Registry | W2 | OUF-E2E-014 | Onboarding & THS | Integration & QA
UDP-008 | UDP / Urban Object Registry | W4 | OUF-E2E-014 | Onboarding & THS | Integration & QA
UDP-014 | UDP / Urban Object Registry | W5 | OUF-E2E-014 | Onboarding & THS | Integration & QA
ING-007 | Ingestion Runtime | W2 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
ING-010 | Ingestion Runtime | W4 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
ING-012 | Ingestion Runtime | W5 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
ONB-013 | Onboarding & THS | W4 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
SEM-003 | Semantic Registry | W1 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
SEM-004 | Semantic Registry | W1 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
SEM-010 | Semantic Registry | W5 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
UDP-012 | UDP / Urban Object Registry | W4 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
UDP-014 | UDP / Urban Object Registry | W5 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
AUTH-005 | Authorization | W2 | OUF-E2E-015 | Ingestion Runtime | Integration & QA
MCP-008 | MCP Server | W4 | OUF-E2E-016 | Onboarding & THS | Integration & QA
MCP-010 | MCP Server | W5 | OUF-E2E-016 | Onboarding & THS | Integration & QA
THS-001 | Onboarding & THS | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
THS-002 | Onboarding & THS | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
THS-003 | Onboarding & THS | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
THS-004 | Onboarding & THS | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
THS-005 | Onboarding & THS | W3 | OUF-E2E-016 | Onboarding & THS | Integration & QA
THS-006 | Onboarding & THS | W4 | OUF-E2E-016 | Onboarding & THS | Integration & QA
AUTH-005 | Authorization | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
AUTH-006 | Authorization | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
AUTH-008 | Authorization | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
AUTH-009 | Authorization | W3 | OUF-E2E-016 | Onboarding & THS | Integration & QA
GW-002 | Urban API Gateway | W1 | OUF-E2E-016 | Onboarding & THS | Integration & QA
GW-005 | Urban API Gateway | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
GW-008 | Urban API Gateway | W2 | OUF-E2E-016 | Onboarding & THS | Integration & QA
GW-012 | Urban API Gateway | W4 | OUF-E2E-016 | Onboarding & THS | Integration & QA
INT-005 | Integration & QA | W0 | OUF-E2E-016 | Onboarding & THS | Integration & QA
ONB-007 | Onboarding & THS | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
ONB-008 | Onboarding & THS | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
GW-004 | Urban API Gateway | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
GW-007 | Urban API Gateway | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
ING-002 | Ingestion Runtime | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
ING-003 | Ingestion Runtime | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
ING-006 | Ingestion Runtime | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
ING-007 | Ingestion Runtime | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
UDP-003 | UDP / Urban Object Registry | W2 | OUF-E2E-017 | Integration & QA | Integration & QA
UDP-004 | UDP / Urban Object Registry | W3 | OUF-E2E-017 | Integration & QA | Integration & QA
INT-009 | Integration & QA | W3 | OUF-E2E-017 | Integration & QA | Integration & QA
GW-005 | Urban API Gateway | W2 | OUF-E2E-018 | Authorization | Integration & QA
GW-008 | Urban API Gateway | W2 | OUF-E2E-018 | Authorization | Integration & QA
GW-012 | Urban API Gateway | W4 | OUF-E2E-018 | Authorization | Integration & QA
AUTH-005 | Authorization | W2 | OUF-E2E-018 | Authorization | Integration & QA
AUTH-007 | Authorization | W2 | OUF-E2E-018 | Authorization | Integration & QA
AUTH-008 | Authorization | W2 | OUF-E2E-018 | Authorization | Integration & QA
AUTH-011 | Authorization | W4 | OUF-E2E-018 | Authorization | Integration & QA
UDP-008 | UDP / Urban Object Registry | W4 | OUF-E2E-018 | Authorization | Integration & QA
SEM-004 | Semantic Registry | W1 | OUF-E2E-019 | Semantic Registry | Integration & QA
SEM-010 | Semantic Registry | W5 | OUF-E2E-019 | Semantic Registry | Integration & QA
ONB-005 | Onboarding & THS | W2 | OUF-E2E-019 | Semantic Registry | Integration & QA
ONB-007 | Onboarding & THS | W2 | OUF-E2E-019 | Semantic Registry | Integration & QA
ING-002 | Ingestion Runtime | W2 | OUF-E2E-019 | Semantic Registry | Integration & QA
ING-007 | Ingestion Runtime | W2 | OUF-E2E-019 | Semantic Registry | Integration & QA
UDP-005 | UDP / Urban Object Registry | W2 | OUF-E2E-019 | Semantic Registry | Integration & QA
UDP-012 | UDP / Urban Object Registry | W4 | OUF-E2E-019 | Semantic Registry | Integration & QA
ONB-004 | Onboarding & THS | W1 | OUF-E2E-020 | UDP / Urban Object Registry | Integration & QA
ING-003 | Ingestion Runtime | W2 | OUF-E2E-020 | UDP / Urban Object Registry | Integration & QA
ING-007 | Ingestion Runtime | W2 | OUF-E2E-020 | UDP / Urban Object Registry | Integration & QA
UDP-002 | UDP / Urban Object Registry | W1 | OUF-E2E-020 | UDP / Urban Object Registry | Integration & QA
UDP-005 | UDP / Urban Object Registry | W2 | OUF-E2E-020 | UDP / Urban Object Registry | Integration & QA
UDP-006 | UDP / Urban Object Registry | W2 | OUF-E2E-020 | UDP / Urban Object Registry | Integration & QA
UDP-015 | UDP / Urban Object Registry | W3 | OUF-E2E-020 | UDP / Urban Object Registry | Integration & QA
INT-004 | Integration & QA | W0 | OUF-E2E-021 | Integration & QA | Integration & QA
INT-006 | Integration & QA | W1 | OUF-E2E-021 | Integration & QA | Integration & QA
AUTH-002 | Authorization | W1 | OUF-E2E-021 | Integration & QA | Integration & QA
AUTH-009 | Authorization | W3 | OUF-E2E-021 | Integration & QA | Integration & QA
GW-002 | Urban API Gateway | W1 | OUF-E2E-021 | Integration & QA | Integration & QA
GW-012 | Urban API Gateway | W4 | OUF-E2E-021 | Integration & QA | Integration & QA
MCP-003 | MCP Server | W2 | OUF-E2E-021 | Integration & QA | Integration & QA
MCP-002 | MCP Server | W1 | OUF-E2E-022 | Integration & QA | Integration & QA
MCP-003 | MCP Server | W2 | OUF-E2E-022 | Integration & QA | Integration & QA
GW-003 | Urban API Gateway | W1 | OUF-E2E-022 | Integration & QA | Integration & QA
GW-005 | Urban API Gateway | W2 | OUF-E2E-022 | Integration & QA | Integration & QA
AUTH-003 | Authorization | W1 | OUF-E2E-022 | Integration & QA | Integration & QA
AUTH-005 | Authorization | W2 | OUF-E2E-022 | Integration & QA | Integration & QA
INT-007 | Integration & QA | W1 | OUF-E2E-022 | Integration & QA | Integration & QA
GW-006 | Urban API Gateway | W2 | OUF-E2E-023 | Urban API Gateway | Integration & QA
GW-013 | Urban API Gateway | W5 | OUF-E2E-023 | Urban API Gateway | Integration & QA
ING-011 | Ingestion Runtime | W4 | OUF-E2E-023 | Urban API Gateway | Integration & QA
MCP-003 | MCP Server | W2 | OUF-E2E-023 | Urban API Gateway | Integration & QA
MCP-006 | MCP Server | W2 | OUF-E2E-023 | Urban API Gateway | Integration & QA
INT-004 | Integration & QA | W0 | OUF-E2E-023 | Urban API Gateway | Integration & QA
INT-010 | Integration & QA | W4 | OUF-E2E-023 | Urban API Gateway | Integration & QA
GW-004 | Urban API Gateway | W2 | OUF-E2E-024 | Urban API Gateway | Integration & QA
GW-011 | Urban API Gateway | W3 | OUF-E2E-024 | Urban API Gateway | Integration & QA
GW-013 | Urban API Gateway | W5 | OUF-E2E-024 | Urban API Gateway | Integration & QA
ONB-008 | Onboarding & THS | W2 | OUF-E2E-024 | Urban API Gateway | Integration & QA
INT-010 | Integration & QA | W4 | OUF-E2E-024 | Urban API Gateway | Integration & QA
INT-005 | Integration & QA | W0 | OUF-E2E-025 | Integration & QA | Integration & QA
INT-009 | Integration & QA | W3 | OUF-E2E-025 | Integration & QA | Integration & QA
GW-008 | Urban API Gateway | W2 | OUF-E2E-025 | Integration & QA | Integration & QA
GW-012 | Urban API Gateway | W4 | OUF-E2E-025 | Integration & QA | Integration & QA
MCP-006 | MCP Server | W2 | OUF-E2E-025 | Integration & QA | Integration & QA
MCP-009 | MCP Server | W4 | OUF-E2E-025 | Integration & QA | Integration & QA
ING-007 | Ingestion Runtime | W2 | OUF-E2E-025 | Integration & QA | Integration & QA
ING-011 | Ingestion Runtime | W4 | OUF-E2E-025 | Integration & QA | Integration & QA
UDP-005 | UDP / Urban Object Registry | W2 | OUF-E2E-025 | Integration & QA | Integration & QA
AUTH-008 | Authorization | W2 | OUF-E2E-025 | Integration & QA | Integration & QA

## Semantic Mapping QA
OUF WBS ↔ E2E Semantic Mapping QA | Value | Interpretation
Source WBS | v0.3 | 106 tasks; task/wave/dependency semantics unchanged
Target WBS | v0.4 Semantic Aligned | Only E2E traceability normalized
Canonical E2E | v0.3 | 25 scenarios
Semantic mapping | OUF_WBS_E2E_Semantic_Mapping_v1_0_Reality_Baseline.yaml | Normative task-to-scenario map
Total task-scenario links | 194 | 194
Missing WBS tasks | 0 | Must be 0
Semantic team/module mismatches | 0 | Must be 0
Abstract module-label exceptions | 5 | Reviewed explicit exceptions only
Scope | No MCP/API Verticali/contract semantics changed | Traceability correction only
Scenario | WBS Task | Task Team | Abstract Scenario Label
OUF-E2E-021 | MCP-003 | MCP Server | MCP/Backend
OUF-E2E-025 | ING-007 | Ingestion Runtime | Backend Owner
OUF-E2E-025 | ING-011 | Ingestion Runtime | Backend Owner
OUF-E2E-025 | UDP-005 | UDP / Urban Object Registry | Backend Owner
OUF-E2E-025 | AUTH-008 | Authorization | Backend Owner